## 1.0 Table of Contents
Response Workbook
TMS Managed Services — RFP Vendor Response Template
Complete all tabs in this workbook. Click a section name below to navigate directly to that tab.
# | Section | Description
1.0 | Table of Contents | Navigation and workbook overview
2.0 | Industry Experience | Organizational track record, workforce, and credentials
3.0 | Relevant Experience | Case studies and client references
4.0 | Workforce & Delivery | Service coverage, languages, sites, workforce migration, and offshore phasing
5.0 | Technology Solution | Technology mapping, governance commitments, AI overlays, and efficiency plan
6.0 | Pricing | Rate card, professional services, one-time costs, and pricing assumptions
7.0 | Client Migration | Client-level migration plan and wave sequencing
8.0 | Regulatory Compliance | Regulatory, compliance, and data governance commitments
9.0 | Client EfficiencyAssumption | commitment from the vendor on offshore to onshore mix, consequent labor arbitrage %, cost reduction from AI & Digital Overlays, cost reduction from Productivity gains

## 2.0 Industry Experience
2.0 Industry Experience
Complete Column D for every row. For rows asking for years of experience, enter the number of years and include a brief note on scope or relevant clients. For all other rows, provide a written response. Specific, evidence-based answers are expected.
2.1 — Industry Track Record
Complete Column D for every row. For rows asking for years of experience, enter the number of years and include a brief note on scope or relevant clients. For all other rows, provide a written response. Specific, evidence-based answers are expected.
Area of Experience | What We Are Asking | Vendor Response
Track Record — Financial Services Issuer Services | Describe your organization's overall track record serving card-issuing financial institutions. Include years in market, number of active issuer clients, approximate ACV managed, and any notable performance milestones. | Genpact delivers end-to-end Customer Experience services to global clients across Banking & Financial Services, Fintech & Hi-Tech, Manufacturing, Life Sciences, Healthcare, CPG, and Insurance. We manage $130Bn+ in retail lending assets and support 600+ processes across the retail banking value chain, including Omni-Channel Customer Service, Contact Centre Analytics & Dashboards, Account Maintenance, Query & Dispute Management, Fraud, Payments, Billing and Refunds, Chargeback Processing, Ongoing AML Screening and Transaction Monitoring, KYC Refresh/EDD for High-Risk customers, and Service to Sales. Our operations span Omni-Channel Operations, Transformation Services, and Customer Experience Analytics, with proven delivery across prepaid, HCCA, and fraud authentication and verification services. Globally, we drive large-scale transformation for Tier 1 banks — achieving a 50%+ productivity improvement in the first four years of a five-year strategic partnership across Personal, Commercial, Business Banking, Mortgages, Payments, Collections, and Financial Crime. Our global footprint combines consulting, digital, technology, analytics, and intelligent operations, leveraging agentic AI, advanced ML models, GenAI, and scalable cloud infrastructure to deliver operational efficiency, enhanced customer experience, and digital modernization across industries, domains, and geographies. Notable performance milestones include an Industry leading NPS score of 84 and $300+ million impact delivered.
4th Party / Sub-Contractor Management | Describe your approach to managing sub-contractors used in delivering TMS services. Confirm: (1) whether sub-contractors would be used on this engagement, which subcontractors would be used and where work would be performed; (2) your SLA flow-down mechanism; (3) whether the client retains audit rights over sub-contractors. | No subcontractors shall be engaged in connection with this engagement except for Genpact affiliates, which shall be identified and set forth in the applicable Statement of Work.
Years of Experience — Risk Mitigation | How many years has your organization delivered end-to-end risk mitigation covering fraud, collections, disputes, and credit bureau management. Report the number of years your organization has continuously operated this function. Do not sum individual staff years across people — report the longest unbroken period your organization has actively delivered this service. | Genpact has been providing fraud prevention and dispute operations solutions to various banking and capital markets clients over the last 25+ years . The solutions provided by Genpact cover the entire end to end fraud prevention lifecycle including fraud related inbound/outbound calls/chats (includes customer verification, transaction review, case intake, account actions) , detection alert review, alert investigation, and account actions. Our dispute operations front operations capabilities include dispute intake through various channels including calls, email, and chat channels. This includes identifying the dispute category and creating cases for back-office operations. In back-office operations we support dispute investigation, chargeback eligibility checks, chargeback assessment, documents review, chargeback management from 1st chargeback to arbitration support for our clients. Our fraud recovery teams are experienced in reviewing and validating cases and managing recoveries. We are a team of 10,000 + fraud and dispute management professionals, operating out of 10 centers across the globe. COLLECTIONS: Genpact brings over 25+ years of global collections experience, delivering measurable outcomes through digital, data, and AI‑led operations across 30+ countries and 52+ languages. Genpact supports end‑to‑end collections covering customer engagement, hardship handling, compliance, disputes, analytics, and escalations. Proven benchmarks include up to 20–30% efficiency gains, 15% improvement in cash collected, 5% reduction in complaints and 35-40% Self serve/ Containment. Genpact combines deep domain expertise, scalable cloud platforms, and agentic AI to optimize recovery, compliance, and customer experience.
Years of Experience — Customer Care | How many years has your organization delivered customer care for card programs (commercial, consumer credit, debit, retail, loyalty, healthcare, prepaid). Scope includes: IVR and live agent handling, multilingual and after-hours support, lost/stolen servicing, and loyalty programs. Report the number of years your organization has continuously operated this function. Do not sum individual staff years across people — report the longest unbroken period your organization has actively delivered this service. | Genpact began doing customer care as a stand alone company on 2005 but before that was doing this work as part of GE since 1997. We have relationships with financial services companies where we have been doing customer care work that have existied for over 17 consecutive years. Genpact services all types of card products, credit, debit, pre-paid, BNPL, co-branded and retail. Our global footprint allows us to provide 24/7/365 servicing across all channels, voice, chat, email, secured messaging and social media. Our team proivide service across over 50 languages and we maintain best in class language translation technology that allows us to service various languages from anywhere in the world.
Years of Experience — Back Office | How many years has your organization delivered back-office processing for card programs. Scope includes: imaging, correspondence processing, payment research, balance transfers, credit balance refunds, account maintenance, general ledger (GL) balancing and settlement, reconciliation of GL accounts, and returned mail processing. Note: application processing is not in scope for this engagement. Report the number of years your organization has continuously operated this function. Do not sum individual staff years across people — report the longest unbroken period your organization has actively delivered this service. | Genpact has been delivering large scale back office processing for card programs for 25+ years, supporting Tier 1 global banks, card issuers and fintech’s across highly regulated environments. Our end to end operations capabilities span onboarding & issuance, servicing & maintenance, payment processing, settlements, and reconciliations, underpinned by strong controls and compliance. Our back office capabilities cover the full breadth of card program support, including imaging and document digitization, correspondence processing, exception handling, account maintenance, GL processing and reconciliations, returned mail handling, and compliance driven reporting, delivered across hundreds of processes supporting billions in assets and transactions globally. We combine deep domain expertise with Agentic AI, GenAI enabled solutions, predictive models, and advanced workflow orchestration to drive straight through processing, reduce manual effort, and improve accuracy. This integrated model has delivered higher STP, significant AHT reduction, lower rework, and improved reconciliation auto match rates, enabling scalable, resilient, and cost efficient card operations.
Years of Experience — Client Operations Oversight | How many years has your organization delivered structured client-facing operational support. Scope includes: day-to-day client inquiry and escalation management, monthly and quarterly business reviews, and SLA monitoring. Report the number of years your organization has continuously operated this function. Do not sum individual staff years across people — report the longest unbroken period your organization has actively delivered this service. | We have 29 years of experience. Our organization has continuously delivered structured, client‑facing operational support since 1997, beginning as a captive unit to GE Capital (GECIS), where we supported GE businesses and their end clients across multiple service lines. This model required day‑to‑day inquiry handling and escalation management, formal SLA tracking, and structured monthly and quarterly operational reviews with business stakeholders. Following our spin‑off from GE in 2005, these same capabilities have been delivered without interruption to external clients globally.
Number of Active Financial Services Clients | How many active financial services clients does your organization currently serve? Break out by client type (issuer, acquirer, payments processor, other) where possible. | 300+ clients, we deliver the full spectrum of services. Genpact offers a range of products and services for digital payments, customer service, fraud, consumer and treasury management payments, cash applications, invoice to cash, lockbox/checks and ecommerce services, but does not operate a payments platform. We bring expertise in experience design, AI, data and technology to build new payments products, manage technology services and transform and run operations.
Countries of Operation | In which countries do you currently deliver contact center or back-office services? Please list all the countries and sites you currently support. For each, indicate whether the site is company-owned or sub-contracted. | Below are our Key contact center delivery hubs: Philippines - Company Owned India - Company Owned Romania - Company owned Poland - Company Owned Guatemala - Company owned
Languages Supported | Which languages do you currently support across your delivery network? List associated delivery locations. Of particular relevance: English (US, CA, UK), Spanish (US), French-Canadian, German, Dutch, Portuguese. | English: United States (Atlanta; Wilkes-Barre; Richardson; Bloomington; Jacksonville; Danville; Chicago; Portland; Bentonville), Canada (Mississauga), United Kingdom (Belfast; Manchester). Spanish: United States (Atlanta; Wilkes-Barre; Richardson; Bloomington; Jacksonville; Danville; Chicago; Portland; Bentonville), United Kingdom (Manchester), Romania (Bucharest; Cluj), Poland (Lublin; Krakow; Katowice), Hungary (Budapest), Germany (Munich), Mexico (Juarez; Guadalajara), Costa Rica (Heredia), Guatemala (Guatemala City). French-Canadian: Canada (Mississauga). German: United Kingdom (Manchester), Romania (Bucharest; Cluj), Poland (Lublin; Krakow; Katowice), Hungary (Budapest), Germany (Munich), Egypt (Cairo). Dutch: United Kingdom (Manchester), Romania (Bucharest; Cluj), Poland (Krakow), Netherlands (Hoofddorp), Hungary (Budapest). Portuguese: China (Shanghai), Romania (Bucharest; Cluj), Poland (Lublin), Mexico (Monterrey), Brazil (Uberlandia).
Overall Workforce | What is your total headcount across all geographies? Break out by: (1) front-office agent FTE; (2) back-office agent FTE; (3) support FTE (QA, WFM, Training, Management, Analytics); (4) approximate onshore / nearshore / offshore split (%). | Our global delivery model is supported by a scalable workforce with strong presence across customer operations and collections. Genpact has over 140,000 employees serving various geographies and customers. Breakdown by function: • Front-office agent FTE : ~65–70% • Back-office agent FTE and Support FTE : 30-35% Geographic delivery mix: • Offshore: ~85% • Nearshore: ~10% • Onshore: ~5% This operating model enables us to deliver cost-efficient, scalable, and high-quality services while maintaining strong operational governance, domain expertise, and 24/7 coverage aligned to client requirements.
Agent Attrition — Last 3 Calendar Years | What were your voluntary agent attrition rates for each of the last three calendar years? Break out by geography where materially different. | We have maintained voluntary attrition within competitive industry benchmarks, with a clear downward trend over the past three years driven by focused investments in employee engagement, career development, and frontline leadership effectiveness. Our overall voluntary attrition has improved from approximately 24–26% in 2023, to 20–22% in 2025, reflecting the impact of targeted retention initiatives, structured learning pathways, and enhanced employee experience programs.
Average Agent Tenure | What is your average agent tenure overall? Break out by primary function where available: Customer Service, Fraud Operations, Disputes & Chargebacks, Debt & Collections, Back Office, and Risk & Compliance. | Our workforce demonstrates a balanced mix of stability and agility, supported by structured training programs, clear career progression pathways, and ongoing employee engagement initiatives. Overall average agent tenure: ~2.5–3 years
Agent Qualifications | Optional. Are there any industry-relevant certifications, training frameworks, or accreditations held by your workforce that are applicable to financial services contact center operations? | Our workforce is enabled through a strong blend of industry-recognized certifications such as CFE and ACAMS, structured training frameworks, and role-based accreditations aligned to fraud and dispute operations. We have institutionalized talent development through our flagship FCRM Talent Academy. This program partners with academic institutions to scout early talent and combines deep SME-led training with curated content and real-world case studies developed alongside our training partners. Our investment in external certifications is further strengthened by robust internal accreditations across fraud, disputes, and quality roles—ensuring strong customer empathy in the front office and rigorous investigation and control discipline in the back office.

## 3.0 Relevant Experience
3.0 Relevant Experience
Provide three case studies and three client references on comparable engagements. Case studies should reflect large-scale, regulated financial services BPO. At least one must involve a migration of 300+ FTE.
3.1 Case Studies
Select engagements that reflect large-scale, regulated financial services BPO. At least one must involve a migration of 300+ FTE. Include one engagement where challenges were encountered — describe what happened and how they were resolved.
# | Industry & Client Type | Scale (FTE / Volume) | Services Provided | Geographies & Languages | Transformation Levers Applied | Measurable Outcomes | Challenges & Resolution
1 | Banking – FinTech | 1300+ | Disputes Fraud Operations, Lending Operations, Collections | US, India, Philippines ¦ English ¦ Spanish + 20 + additional languages | • Leveraged Genpact’s gold‑standard rebadge playbook • Upskilled rebadged employees on Lean Six Sigma • Deployed digital MIS and performance reporting suite • Implemented AI‑powered agent performance tools • Drove volume elimination through AI‑ and digital‑led insights and automation | • 98% rebadge success • $23M+ cost‑out by Year 2 • 70% reduction in chargeback write‑offs • 17% improvement in call containment driven by AI‑led intervention | • Extremely tight rebadge timelines • Aggressive cost‑out pressure • Legacy backlog and escalations • Addressed through governance‑driven rebadge playbook, rapid workforce stabilization, and digital enablement
2 | Global Banking - Retail and Commercial Bank | 2,300+ | Customer Service (voice & non‑voice), Collections, Fraud Operations, Disputes & Chargebacks, Core Retail & Payments Operations | US, Philippines, India, Guatemala ¦ English (global delivery) | • Global outsourcing delivery model • Intelligent operations enablement • Lean Six Sigma frameworks • Automation and analytics overlays • Digital case management • Operating model standardization | • 20% improvement in customer experience metrics • Industry‑leading NPS of 84 • 70% reduction in delinquency • Improved productivity across customer operations | • Highly fragmented global operations • Manual processes and capacity strain • Addressed through consolidated global delivery, standardized operating model, and digital/analytics‑led productivity levers
3 | Leading European automotive finance institution | 430+ FTEs supporting 7 European markets | Customer Service, Accounting, Collections | Europe (multi‑country) ¦ French, Italian, Spanish, Portuguese, Dutch, Swedish, English | • GenAI‑enabled knowledge assist • AI‑powered coaching • AI‑based Nudge Coach for performance monitoring • GenAI language neutralization platform • Azure AI extraction solution • Customized Amazon Connect telephony solution & GenAisys • Enterprise‑scale RPA program | • 25% productivity lift through AI‑driven automations • CSAT improvement from 3.0 to 3.8 • Increased adoption of agentic AI for transformation • 20% improvement in Voice KPIs (Collections) • 25% training time reduction for CS & Collections voice agents | • Fragmented country‑specific operations • High cost and inconsistent quality • Multiple local providers and technology gaps • Addressed through centralized AI‑first operating model and standardized workflows
3.2 Client References
References must be contactable and from current or former financial services clients on comparable engagements. At least one reference should be able to speak to a transformation or large-scale migration program.
# | Company Name | Reference Name & Title | Contact Information | Nature of Engagement | Additional Notes
1 | Major UK based Retail and Commercial Bank | To be provided later at the time of reference checks. | To be provided later at the time of reference checks. | Transformation embedded managed services.
2 | Large Global FinTech
3 | Leading US Financial Technology company

## 4.0 Workforce & Delivery
4.0 Workforce & Service Delivery
This tab covers eigh areas: (1) language capabilities, (2) rebadging scope (3) rebadging / offshoring schedule (5) staffing model, (6) cost impacts, (7) SLA Adherance, and (8) Change Management Approach. Responses across sections should be consistent with each other and with your pricing in sheet 6.0.
4.1 Language Capabilities
Confirm your ability to support each language. For each language, list the delivery location(s) you would use to support it.
Language | Can You Support? (Y/N) | Primary Delivery Location | Secondary Location | Tertiary Location | Volume / Threshold Notes
English (US) | y | y | y | y | y
English (UK) | y | y | y | y | y
English (Canada) | y | y | y | y | y
Spanish (US) | y | y | y | y | y
French-Canadian | y | y | y | y | y
German | y | y | y | y | y
Dutch | y | y | y | y | y
Portuguese | y | y | y | y | y
4.2 Site Rebadge Approach
TMS currently operates across seven sites across North America (North America) and Europe, Middle East & Africa (EMEA). For each site, indicate your intended approach. Headcount figures will be provided in the data appendix.
Site | Region | Intend to Take Over Site? (Y/N) | Target Transition Date | Approach (Workforce Only / Site + Workforce / Neither) | Approx. FTE at Site (post-transition) | Considerations & Assumptions
US — Columbus, GA | North America | Yes, our intention is to take over both the workforce and the site, wherever it makes strategic sense. We look forward to discussing this further.
Canada — Sudbury | North America
Philippines — Manila | North America / Offshore
UK — Milton Keynes | EMEA
UK — Coventry | EMEA
Netherlands — Barneveld | EMEA
Germany — Hamburg | EMEA
4.3 Employee Transition Terms
State your position on each commitment. Note conditions or constraints where you cannot fully commit.
Rebadging Ease of Transition | Response
Same salaries offered to rebadged employees? (Y/N) | Future compensation will be based on country/state regulation
Same benefits offered to rebadged employees? (Y/N) | Future benefits will be based on country/state regulation
Retention bonus to be paid? (Y/N) | To be determined as part of the solution for critical talent
Severance to be paid if employees are downsized? (Y/N) | Severance to be paid based on the country/state regulation and commercial discussions
4.4 Legacy IT & Site Asset Acquisition
For each asset, confirm acquisition intent and proposed transfer date. Where declining, state your transition assumptions.
Legacy IT and Site Infrastructure | Will the technology be acquired? (Y/N) | Transfer Date | Genpact Assumptions
Technology Licenses | N | Target Date to be discussed and agreed upon mutually with client. | Genpact assumes that all required line‑of‑business applications, Office productivity software, and collaboration tools will be provided, supported, and appropriately licensed by FIS. We further assume that Genpact users will operate either on FIS standard image laptops, as in previous Gamma waves, or within an FIS‑provided VDI environment.
Laptops | Y | Target Date to be discussed and agreed upon mutually with client. | This decision depends on the endpoints’ acceptable operating condition, warranty coverage, and fair market value. We assume that the endpoints included in the asset transfer scope will have sufficient remaining useful life, be in good working condition, and be covered by an adequate warranty. The laptop transfer can be addressed at a later stage, consistent with the approach followed during previous Gamma waves once the asset inventory is shared and IT solution approach is finalized
Site specific networking components | N | Target Date to be discussed and agreed upon mutually with client. | As part of our proposal, we have assumed that FIS's network services will continue at the site. Networking component transfer is not considered in the current proposal, and we can explore with a proper DD, however, is not included in our standard proposal and any adaptation is a joint effort and decision as it impacts costs
Other | N | Target Date to be discussed and agreed upon mutually with client. | As part of our proposal, we assume that FIS network services will continue to be available at the site. Any additional component transfers, including networking, are not included in the current proposal. Such transfers may be explored following appropriate due diligence; however, they fall outside the scope of our standard proposal. Any required adaptations would be subject to joint discussion and agreement, as they have cost implications.
4.5 Role-Level Rebadge & Retention Scope
For each function and site, confirm whether staff are in scope for rebadging and retention bonus eligibility.
Will these resources be rebadged? (Y/N)
Functions Specification | US — Columbus, GA | Canada — Sudbury | Philippines — Manila | UK — Milton Keynes | UK — Coventry | Netherlands — Barneveld | Germany — Hamburg | In-scope for retention bonus? Y/N
WFM | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Training | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Quality | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Customer Service | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Loyalty | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Disputes Inbound | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Fraud Inbound | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Fraud Outbound | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Fraud Strategy | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Back Office Disputes | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Off Phone | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Accounting | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Reporting | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Collections | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
IVR/Tech | Y | Y (Rehire) | Y | Y | Y | Y | Y | To be determined as part of the solution for critical talent
Senior Leadership | Y | Y (Rehire) | Y | Y | Y | Y | Y
4.6 Location Model
For each service tower, describe how you propose to rebadge or offshore and nearshore delivery over the contract term in a location migration plan. Vendor to add additional sites locations the work will be transitioned to as necessary. Vendors should propose the delivery footprint they believe is optimal to achieve the efficiency outcomes described in the RFP, within the client and regulatory constraints identified. Clearly state your assumptions and the sequencing rationale. Note: your full list of current operating locations should be declared in tab 2.0 under Countries of Operation and not necessarily repeated here.
Current Host Location | Future Host Location | End State, How many FTE will Remain at this location? (Provide as a % of the current site FTE counts)
US — Columbus, GA | US — Columbus, GA | 10.6%
Canada — Sudbury | Canada — Sudbury | 26%
Philippines — Manila | Philippines — Manila | 2062%
UK — Milton Keynes | UK — Milton Keynes | 10%
UK — Coventry | UK — Coventry | 10%
Netherlands — Barneveld | Netherlands — Barneveld | 30%
Germany — Hamburg | Germany — Hamburg | 30%
Add additional locations as desired | India — Pune | 330%
4.7 SLA & KPI Improvement Commitments
Demonstrate the expected improvement in SLAs/KPIs over time, from transition through steady state. Proposed commitments may be incorporated into contractual service level schedules.
SLA/KPI | Current Levels | Future Levels | Improvement Approach | Time to improvement
LOB | AHT (KPI) | AHT (KPI) | Vendor to provide approach to improving SLA / KPI | Vendor to provide improvement timing
Blended Fraud Inbound | 687 | 657.9399 | Combine RTA, routing optimization, break staggering, and call blending during peaks Align schedules to interval level demand, prioritize high SLA queues, overflow tuning logic Improve interval coverage, prioritize queues, reduce wait time via better distribution Knowledge base improvement, call flow simplification, agent coaching Reduce wait time via routing + callback option + peak handling | Phase 1: Baseline Assessment (0–6 Months) Post Go-Live Baselining: Each transitioned wave will be baselined for volume, AHT, SLAs and KPIs over ~6 months. Establish a robust performance baseline by analyzing actual AHT, SL, ASA, and demand patterns at interval level. Identify gaps between planned vs. actual capacity, adherence, and queue performance to understand true on-ground dynamics. Phase 2: Opportunity Identification & Strategy Design (2–3 Months) Evaluate key improvement levers across scheduling, RTA, routing, and process efficiencies. Prioritize high-impact interventions and define a structured action plan aligned to SLA targets and operational constraints. Phase 3: Implementation & Controlled Optimization (Ongoing) Execute identified initiatives in a phased manner with continuous monitoring against baseline metrics. Stabilize performance through controlled rollout, real-time governance, and iterative refinements to ensure sustained SLA improvement.
Dedicated Fraud Inbound | 632.12 | 605.3813
Blended Disputes Inbound | 433 | 414.6841
Dedicated Disputes Inbound | 530.45 | 508.012
Blended Customer Service | 339 | 328.83
Dedicated Customer Service | 377.91 | 366.5727
Loyalty | 425 | 412.25
Others Overall | 472.33 | 458.1601
NA-3 | 521.18 | 497.7269
NA-2 | 749.31 | 715.591
NA-5 | 423.58 | 410.8726
NA-1 | 441.28 | 428.0416
NA-14 | 630.69 | 602.309
EMEA-UK-2 | 541.21 | 524.9737
EMEA-UK-3 | 500.8 | 485.776
EMEA-UK-5 | 465.84 | 452.7965
EMEA-UK-4 | 402.74 | 391.4633
EMEA-Germany-1 | 421.18 | 409.387
EMEA-UK-7 | 383.95 | 373.1994
EMEA-Dutch-1 | 287.32 | 283.0102
EMEA-Dutch-2 | 304.09 | 299.5286
EMEA-UK-1 | 497.41 | 482.4877

## 5.0 Technology Solution
5.0 Technology Solution
This tab covers four areas: (1) technology capability mapping — current TSYS applications and expected future-state are pre-populated for reference; respond with your proposed solution and migration approach; (2) technology governance commitments; (3) AI overlay capabilities; (4) Technology Costs You Are Willing to Fund and (5) a Technology responsibility Matrix between yourself and FIS/TSYS; The migration approach and target architecture columns are intentionally open. FIS is not prescribing a migration methodology or architecture pattern. Vendors should propose the approach they would actually use based on the current and future-state stack shown. Responses that reflect a genuine assessment of the TSYS-to-FIS technology context will be evaluated more favorably than generic migration frameworks.
5.1 Technology Capability Mapping & Migration Plan
Columns D and E show the current TSYS application and the expected future-state application for reference. Where no future-state equivalent exists, the TSYS application will be retained. Provide your proposed solution, migration approach, and costs.
Capability | Technology Type | Current TSYS Application | Future-State Application (if no equivalent, TSYS retained) | Phasing Strategy | Proposed Sequencing | Migration Approach | Target Architecture Pattern | Data Migration Approach | Estimated Start Date | Cutover Duration | Key Dependencies | Key Risks | Capbility/Tech stack/Sizing Image 1.a
Communications Management | Voice (Inbound/Outbound) | Avaya (CM, AAEP, AES, CBA, Session Mgr, SBCE) | NICE CXone | We propose a Pod based approach with the first pod migrated as a pilot followed by other pods in waves Details shared in slide title: "Technology Capability Mapping & Migration Plan" | Pods are sequenced based on combination of Client Effort Size and Criticality. In US Sequencing has been planned with a balance of High Criticality and Low Criticality clients in each Pod. In Pilot phase will have following things are prioritised (Base platform + IVR(DTMF, Speech), Chat Skill based Routing, QM, Agent Desktop, CTI-CRM Integration (TCS –Pega) OOTB reports) | In Pilot phase which will be Live on Month 4 will have Inbound /Outbound Featue with featues listed in S size in the slide attached in Cell P11 | Nice Cxone CCaaS with Microsoft Agentic IVA | We will be focused on primarily configuration and routing logic replication as per the current system | Month 1 ( Discovery) Month 2 started | Inbound /Outbound ready will be ready in Month 4 and Cutover will happen for each client as part of the Plan for each Pod. | Telecom carrier readiness and number porting must be aligned. However we will have still retain the number ported to the current Avaya system, we will be establishing, SIP trunk between Avaya & Nice CxOne for call routing/forwarding. Once Client mapped to that DID/TFN moved completely to the Nice CxOne after 15 days of stable operations, will get the number ported to Lumen connected to Cxone | Risk of call drops or routing errors during initial cutover. To handle this initially we would recommend doing call transfer to Avaya to CxOne forward on SIP Trunk. When stabilized then perform actual Number Migration
Communications Management | Chat / Secure Messaging | AWS Connect (in deployment) | Microsoft Dynamics/MS Call studio | Phase 1 : (Enable Early) Enable digital channels early to drive deflection and reduce voice dependency. | Pods are sequenced based on combination of Client Effort Size and Criticality. In EMEA Sequencing has been planned by sequencing Large Workload Client between smaller workload clients | Incremental deployment leveraging existing Amazon Connect setup. | Cloud CCaaS | We will be focused on primarily configuration and routing logic replication. | Currently Planned for Month 10 but this can be prioritized if needed | Cutover will happen for each client as part of the Plan for each Pod. | Integration with CRM and authentication systems. | Low adoption if customer journeys are not optimized.
IVR / CTI | Touchpad IVR | Avaya Aura Experience Portal | NICE CXone (IVR module) | Phase 1 : (Rebuild flows) critical IVR journeys first to ensure continuity of self-service. | Rebuild flows | Replatform IVR flows into NICE CXone with improved design. | IVR modernization /Optimization | No migration required as flows will be redesigned. | Month 2 | 3-4 weeks | IVR design sign-off and testing cycles. | Customer drop-offs if IVR flows are not intuitive.
IVR / CTI | Conversational / AI-based IVR | AWS Connect (in deployment) | AWS Connect | Phase 2 : Introduce conversational AI (IVA) after stabilizing DTMF flows. | Introduce AI Powered Chat & Voice | Greenfield build using AWS AI/ML services for NLU. | AI-first powered by AWS COnnect | No legacy migration; new models and intents will be created. | Month 3 | 4-6 weeks | Availability of training data and NLP models. | Accuracy challenges impacting customer experience.
| Screen Pop with Call / Contact | Avaya CTI / Avaya Workspaces (EMEA) | NICE CXone (screen pop module) | Phase 2 : Enable screen capture after stabilizing agent desktop. | Replicate logic | Lift-and-optimize approach to ensure business continuity. | Omnichannel routing | No data migration; routing rules recreated. | Month 2 | 2-3 weeks | Accurate mapping of skills and queues. | Misrouting leading to increased AHT.
Routing | Skills-Based Routing | Avaya CM / AES | NICE CXone | Phase 2: (Lift & Optimize) Replicate existing routing logic first, then optimize for efficiency. | Enhance with AI | Phased rollout of AI-driven decisioning capabilities. | AI-driven routing | No migration; new logic implemented. | Month 3 | 3-4 weeks | Customer data availability and integration. | Incorrect routing logic impacting experience.
Routing | Advanced Routing (customer attribute-based) | Avaya CM / AES | NICE CXone | [5 empty] | Month 2 | 2 weeks
CRM / Case Management | Customer Authentication | Avaya CTI / step-up auth tools | NICE CXone | Phase 2 : Enhance routing with AI once baseline routing is stable. |  | Enable step-up authentication flows in initial phases. | Integrated CX | No major migration; reuse existing authentication data. | Month 4 |  | Security and compliance approvals. | Authentication failures impacting customer trust.
Agent Desktop | Agent Desktop Simplification / Consolidated Desktop | TS1 / TS2 Mainframe Green Screens; TCS (Pega) | Digital Servicing Platform | Phase 1 :Integrate authentication early to ensure secure interactions. | Roll out to pilot agent groups before enterprise deployment. | Rebuild desktop using modern UI and API integrations. | Secure, integrated authentication layer across channels. | API-based integration with existing authentication systems. | Month 2
QA — Recording & Scorecards | Call / Contact Recording | Avaya/Verint WFO; NICE Call Recording (North America); Avaya/Verint WFO (EMEA) | NICE CXone (recording module) | Phase 1 :Migrate recording capabilities alongside voice migration. | Migrate recording | Parallel recording during transition to ensure compliance. | Cloud-based recording and compliance architecture. | Optional migration of historical recordings. | Month 3 |  | Storage and compliance requirements. | Data loss or compliance gaps.
| Screen Capture | Avaya/Verint WFO; Desktop & Process Analytics (EMEA) | NICE CXone | Phase 2 : Enable screen capture after stabilizing agent desktop. | Re-enable | Re-enable functionality within NICE ecosystem. | Integrated QA and monitoring framework. | Low migration; mostly configuration. |  |  | Agent desktop compatibility. | Performance impact on agent systems.
| Quality Scorecard & Review | Avaya/Verint WFO (Quality Monitoring, Form Designer) | NICE CXone | Phase 2 :Enable Nice QA component | Re-enable | Re-enable functionality within NICE ecosystem. | Integrated QA and monitoring framework. | Low migration; mostly configuration.
Speech & Text Analytics | Compliance Monitoring | Avaya/Verint WFO (compliance recording) | NICE CXone | Phase 1 :Introduce compliance analytics early to ensure regulatory adherence during migration. | Enable compliance recording and analytics for priority processes first. | Migrate to NICE CXone compliance module with parallel validation. | AI-powered speech and text analytics with real-time compliance monitoring on NICE | Optional migration of historical recordings; focus on forward-state analytics. | Optional migration of historical recordings; focus on forward-state analytics. |  | Regulatory requirements and QA alignment. | Compliance gaps or missed recordings during transition.
Workforce Management | Strategic & Tactical Forecasting | Avaya/Verint WFO (Strategy Planner + WFM) | NICE CXone (WFM module) | Phase 1 :Stabilize operations first, then transition forecasting and scheduling capabilities. | Migrate forecasting models followed by scheduling and intraday management. | Phased migration with parallel run to validate forecast accuracy. | Cloud-based WFM with AI-driven forecasting and real-time optimization on NICE | Migrate historical data for baseline forecasting models. | Migrate historical data for baseline forecasting models. |  | Historical data quality and integration with CCaaS. | Forecast inaccuracies impacting staffing and service levels.
5.2 Technology Governance Commitments
For each commitment below, state your position clearly. Where you cannot fully commit, describe the conditions or constraints that apply.
Requirement | Vendor Position (Commit / Partial / Cannot Commit) | Details, Conditions, or Constraints
Confirm you will provide open APIs with no data lock-in and full interoperability. | Commit
Confirm the FIS/TSYS retains full ownership of all data at all times, including during and after transition. | Commit
Confirm no proprietary data formats will be used — all data exportable in standard formats at any time. | Commit
Confirm full data extraction rights upon contract exit, at no additional cost to the client. | Commit
Confirm you can provide a side-by-side coexistence environment for a minimum 12-month dual-run period. | Commit
Confirm you will fund technical debt remediation where your technology introduction creates new technical debt. | Partial Commit | We will remediate technology-induced technical debt, subject to scope alignment and agreed commercial terms.
Confirm you will provide AI governance documentation covering bias monitoring, model drift, and explainability for all AI tools deployed. | Commit
Confirm AI overlays can be integrated via API without requiring migration of core telephony or processing platforms. | Commit
Confirm the client retains ownership of telephony infrastructure and IVR design unless explicitly agreed otherwise. | Commit
Confirm a full coexistence architecture plan will be provided prior to go-live, covering the full transition period. | Commit
Confirm all tooling (including AI Overlays) will be pre approved by the FIS/TSYS Governance team, comprised of architecture, AI Governance and Security Operation, prior to implementation. | Commit
Confirm you will provide quantified, contractually referenceable projections of AHT reduction, call deflection, and cost impact from AI overlays. | Commit
5.3 AI Overlay Technology
Describe the AI overlay tools you propose to deploy as part of this engagement. For each, describe the capability, quantify the anticipated operational impact, and confirm how it integrates with the existing technology stack. Summarize your total efficiency ambition across all three levers. All figures in USD millions, rounded to one decimal place (e.g. $2.4M). Clearly state which savings are contractually committed.
Tooling & AI Overlay Technologies | Category (e.g. NLP, GenAI, RPA, Predictive) | Description | Primary Value Lever (Digital Efficiencies, Labor Arbitrage, Productivity) | Quantified Impact (e.g. X% AHT reduction, Contact Elimination) | Timeline to Deploy | Integration Method (API / Native / Other) | Proposed Application to Integrate With | Key Assumptions / Dependencies | Total Opportunity ($M relative to Direct Costs) | Year 1 Benefit ($M) | Year 2 Benefit ($M) | Year 3 Benefit ($M) | Steady State (Y4) Benefit ($M) | Steady State (Y5) Benefit ($M) | Steady State (Y6) Benefit ($M) | Steady State (Y6) Benefit ($M) | Contractually Committed? (Y/N) | Can any technologies be decommissioned/rationalized as a result of this AI overlay? Please identify the impacted applications.
Voice Agents IVA ( End to End front to back) office​ | Conversational AI (Agentic) | Multi-agent system (Agents 1–3) handling inbound fraud call intake via Whisper/IVR stream: context assembly from Falcon, transaction validation via CH dialogue, claim creation in DRC, card block/unblock, and NICE call summary. Human-in-the-loop for high-risk whisper flags and edge cases. | Digital Efficiencies / Labor Arbitrage | ~50–55% net FTE reduction on FAM FO agent-handled calls; IVR self-containment 13%→25%+; eliminates K6 scripting inconsistency and K10 manual NICE logging | Phase 1–2 (Wks 9–44); IVR expand in Phase 2 | API (MCP preferred); computer-use fallback if Falcon API not contracted | Genpact AI Platform; Claude (Anthropic); Falcon MCP; DRC MCP; NICE; Whisper/Voice AI; HITL Review UI | Falcon MCP API contract is critical (no contract = computer-use fallback, STP ceiling drops ~15–20 pts); Whisper STT pipeline custom build; DRC write API required for claim creation; ~107K alerts/month volume baseline | TBD — see staffing model | 0.21157 | 3.9856 | 5.905 | 6.62 | 7.1996 | 7.3371 | 7.4534
AI Chat Agents​ | Conversational AI (Agentic) | Text-based agentic interface for cardholder dispute intake and status inquiries — mirrors Voice Agent logic but via digital channel. Reduces inbound call volume and supports asynchronous dispute handling for T4/T5/T6 case types. | Digital Efficiencies / Labor Arbitrage | Incremental contact deflection on top of IVA; estimated 10–15% reduction in live-agent chat volume (to be validated with FIS volume data) | Phase 2–3 (Wks 25–60) | API (MCP preferred) | Genpact AI Platform; Claude (Anthropic); DRC MCP; HITL Review UI | Dependent on DRC API contract (Phase 0 gate); requires FIS digital channel integration (web/app SDK); volume baseline needed for sizing | TBD — see staffing model | 0.02821 | 0.53142 | 0.78733 | 0.88266 | 0.95994 | 0.97828 | 0.99379
Language Translation Agent | GenAI | Real-time language translation layer integrated into voice and chat agent flows — enables multilingual cardholder support without dedicated bilingual FTE pools. Translates CH input → English for agent processing, and agent output → CH language for delivery. | Labor Arbitrage / Productivity | Eliminates ~100% of premium bilingual staffing costs for supported languages; estimated 5–8% of call volume currently requiring translation support (to confirm with FIS) | Phase 2 (Wks 25–44) | API (MCP preferred) | Genpact AI Platform; Claude (Anthropic); Whisper STT; Voice AI pipeline | Language coverage scope TBD with FIS; accuracy thresholds for regulated call types (Reg Z) must be validated; GDPR/TCPA compliance review required for recorded multilingual calls | TBD | 0.014105 | 0.26571 | 0.39366 | 0.44133 | 0.47997 | 0.48914 | 0.4969
Agent Assist​ | GenAI | Real-time AI co-pilot surfaced on analyst/agent desktop during live calls or case work. Provides next-best-action prompts, auto-populated data from Falcon/DRC/Mainframe, decision rule guidance, and draft response text — reduces cognitive load and AHT without full automation. | Productivity / Digital Efficiencies | 15–25% AHT reduction on assisted calls; quality improvement on HITL-reviewed cases; bridges gap before full straight-through automation is achievable | Phase 1 (Wks 9–24) — parallel to T4 pilot | API (MCP preferred) | Genpact AI Platform; Claude (Anthropic); Falcon MCP; DRC MCP; HITL Review UI | Requires HITL UI build (shared dependency with agentic stack); Falcon read API sufficient (write not required for assist mode); analyst desktop integration (CRM/DRC screen) scoping needed | TBD | 0.10579 | 1.9928 | 2.9525 | 3.31 | 3.5998 | 3.6685 | 3.7267
Auto QA ​Agent | GenAI | Automated quality assurance scoring of 100% of calls and case decisions vs. human sampling (~5–10% today). Evaluates Reg Z / FCBA / UDAAP compliance, script adherence, HITL threshold calibration accuracy, and decision logic consistency. Feeds findings into CAI flywheel. | Digital Efficiencies / Productivity | 100% call/case QA coverage vs. ~5–10% human sampling; estimated 60–70% reduction in manual QA FTE; compliance risk reduction through systematic Reg Z/FCBA audit trail | Phase 1–2 (Wks 9–44) | API (MCP preferred) | Genpact AI Platform; Claude (Anthropic); NICE (call recordings); DRC audit log; AI Quality Lead oversight | NICE API access for call recordings required; structured HITL logging must be instrumented from go-live (non-negotiable CAI design requirement); Reg Z scenario test library to be co-developed with Compliance SME | TBD | 0.014105 | 0.26571 | 0.39366 | 0.44133 | 0.47997 | 0.48914 | 0.4969
Agent Performance Management​ | Data & Analytics | Fast charge contact center agent efficiency and interaction effectiveness through our patented algorithm, that combines 40+ diverse KPIs into a single performance score for every agent through interactive BI to accelerate data to insights to action. | Productivity | ~5-10% AHT Reduction ~8-10% higher QA compliance ~5-10% CX improvement ~10-15% higher sales enablement | Phase 2–3 (Wks 25–60) | Native | Genpact AI Platform; Claude (Anthropic); Falcon MCP; DRC MCP; NICE; Whisper/Voice AI; HITL Review UI, AI Quality Lead oversight, Survey platform | - Access to relevant data sources - Access to storage for input & output data - Access to Analytics infra - Availability of Visualization layer - Access to CCaaS infra - Dedicated SME involvement - Scope includes basic version | TBD | 0.014105 | 0.26571 | 0.39366 | 0.44133 | 0.47997 | 0.48914 | 0.4969
Interaction / Chat Analyzer | Data & Analytics | Optimized customer interactions through insights and recommendations based on contact history enabling personalized engagement​s. | Productivity / Digital Efficiencies | ~5-10% AHT Reduction ~5-8% improved FCR ~10-15% higher QA compliance ~5-10% CX improvement | Phase 2–3 (Wks 25–60) | Native | Genpact AI Platform; Claude (Anthropic); Bedrock, SageMaker, Falcon MCP; DRC MCP; NICE; Whisper/Voice AI; | - Access to relevant data sources - Access to storage for input & output data - Access to Analytics infra - Pipeline to telephony - Access to CCaaS infra - Dedicated SME involvement - Scope includes basic version | TBD | 0.014105 | 0.26571 | 0.39366 | 0.44133 | 0.47997 | 0.48914 | 0.4969
AI Powered Forecasting (AiPlay) | Data & Analytics | AiPLay is an AutoML SaaS application with an easy UX that allows functional stakeholder to build & test machine learning forecasting models via UI | Productivity | Forecasted volume accuracy increment by 2-4% | Month 6 | None - works indpenedently, does not needto integrate with other applications | Not applicable | 1) Successful fitment of requirement once we approval has been received from business and IT team of client 2) Volume dataset required for forecasting and whitelisting of aiPlay tool in client environment | TBD | 0.0070524 | 0.13285 | 0.19683 | 0.22067 | 0.23999 | 0.24457 | 0.24845
AI Coach | NLP, NLU | SAndbox training environment where agents can practice mock calls, chats, concurrent chats as well as screen simulations, interact with mock customers on customized scenarios. | Prodcutivity & Agent Efficiencies | 2 to 4% incease in productivity 15 - 25% speed to proficiency 8-10% uplift in compliance & quality 5-10% C-Sat increase | 4-6 weeks | No integration required with the exception of OKTA or other SSO login protocol | Not applicable | Assumed 16 Topics for NAM & 18 for EMEA. | TBD | 0.014105 | 0.26571 | 0.39366 | 0.44133 | 0.47997 | 0.48914 | 0.4969
Dispute Analyst Modules 1. Predictive Decisioning (Dispute) Agent 2. Dispute Investigation Agent 3. Pre-arbitration Agent 4. Proactive Monitoring and Behavior Pattern Analysis Agent 5. QC Agent | Risk | Agentic Decisioning and actioning of Fraud and non fraud dispute claims with investigation summaries. This solution keeps human in the loop to authorize account actions | Digital Efficiencies | 1. 10-15 % improvement in productivity 2. 5-10% improvement in decision accuracy | Blueprinting, Development , Testing and UAT - 36-44 weeks for end to end development; Basic analysis of claim will be ready in 36 weeks | API | TCS, TS1,TS2, Mastercom/ VROL, Experian/ TransUnion/ LexisNexis, Workflow system | 1, Genpact team will have required level of access to AI Infra for hosting and running AI agents. We will leverage FIS technology stack to develop the solution 2. The solution will leverage API layer mentioned to fetch/ update data with other applications and concerned applications support API calls for data transfer. 3. Client SMEs and relevant knowledgebase will be accessible to Genpact team. 4. Security protocols and access controls will be in place for handling sensitive data. 5. All necessary InfoSec and legal approvals will be secured by the client prior to project execution. |  | 0.23349 | 3.1038 | 4.4692 | 4.9566 | 5.4565 | 5.5629 | 5.6529
Fraud Analyst Modules 1, Predictive Decisioning (Fraud) Agent 2. Fraud labelling Agent 3. Case Management Agent 4. Fraud Investigation Agent 5. Proactive Monitoring and Behavior Pattern Analysis Agent 6. Case Summarization and Case Analytics Agent 7. Customer/ Merchant Outreach Agent | Risk | Agentic decisioning and account actions of fraud alerts. The solution provided investigation sumarries for SMEs to review and authorize account actions. | Digital Efficiencies | 1. 10- 15% improvement in productivity 2. 5-10% improvement in decision accuracy | Blueprinting, Development, Testing and UAT - 36-44 weeks for end to end development; Basic analysis of claim will be ready in 36 weeks | API | TCS, TS1,TS2, Mastercom/ VROL, Experian/ TransUnion/ LexisNexis, , Workflow system | 1, Genpact team will have required level of access to AI Infra for hosting and running AI agents. We will leverage FIS technology stack to develop the solution 2. The solution will leverage API layer mentioned to fetch/ update data with other applications and converned applications support API calls for data transfer. 3. Client SMEs and relrevant knowledgebase will be accessible to Genpact team. 4. Security protocols and access controls will be in place for handling sensitive data. 5. All necessary InfoSec and legal approvals will be secured by the client prior to project execution. |  | 0.15566 | 2.0692 | 2.9795 | 3.3044 | 3.6376 | 3.7086 | 3.7686
Dynamic Workflow Orchestration (Integration with Queues, alerts and cases, initiating customer communication, moving the case through the workflow, role assignment, escalation, OCR/ NLP of Merchant response) | Risk | Implementation of 3- 4 use cases on Case management systems to automate the workflow orchestration | Digital Efficiencies | 1. 6%-8% improvement in productivity 2. 5-10% improvement in decision accuracy | Blueprinting, Devlopment, Testing and UAT - 44- 52 weeks . This can be delivered in Phases | API | TCS, TS1,TS2, Mastercom/ VROL, Experian/ TransUnion/ LexisNexis, Workflow system | 1, Genpact team will have required level of access to AI Infra for hosting and running AI agents. We will leverage FIS technology stack to develop the solution 2. The solution will leverage API layer mentioned to fetch/ update data with other applications and converned applications support API calls for data transfer. 3. Client SMEs and relrevant knowledgebase will be accessible to Genpact team. 4. Security protocols and access controls will be in place for handling sensitive data. 5. All necessary InfoSec and legal approvals will be secured by the client prior to project execution. |  | 0.093396 | 1.2415 | 1.7877 | 1.9826 | 2.1826 | 2.2252 | 2.2612
Single Pane of Glass for Agents | Risk | Single screen module which will gather data from multiple tools & screens to reduce toggling time for users | Digital Efficiencies | 1.5%-8% improvement in productivity 2. 2-5% improvement in Quality | Blueprinting, Devlopment, Testing and UAT - 12 weeks | API | TCS, TS1,TS2, Workflow system | 1, Genpact team will have required level of access to AI Infra for hosting and running AI agents. We will leverage FIS technology stack to develop the solution 2. The solution will leverage API layer mentioned to fetch/ update data with other applications and converned applications support API calls for data transfer. 3. Client SMEs and relrevant knowledgebase will be accessible to Genpact team. 4. Security protocols and access controls will be in place for handling sensitive data. 5. All necessary InfoSec and legal approvals will be secured by the client prior to project execution. |  | 0.093396 | 1.2415 | 1.7877 | 1.9826 | 2.1826 | 2.2252 | 2.2612
Automated account actions and money movement | Risk | Automation of card blocks and account actions on orchestration systems Automation of refunds, provisional credits, write offs. | Digital Efficiencies | 1.5%-8% improvement in productivity 2. 2-5% improvement in Quality | Blueprinting, Devlopment, Testing and UAT - 12 weeks | API | TCS, TS1,TS2, Workflow system | 1, Genpact team will have required level of access to AI Infra for hosting and running AI agents. We will leverage FIS technology stack to develop the solution 2. The solution will leverage API layer mentioned to fetch/ update data with other applications and converned applications support API calls for data transfer. 3. Client SMEs and relrevant knowledgebase will be accessible to Genpact team. 4. Security protocols and access controls will be in place for handling sensitive data. 5. All necessary InfoSec and legal approvals will be secured by the client prior to project execution. |  | 0.046698 | 0.62075 | 0.89384 | 0.99131 | 1.0913 | 1.1126 | 1.1306
API Connections to VROL and Mastercom | Risk | Automated upload / download of information from Visa/Mastercard portals using API connections. Automation of chargeback processing | Digital Efficiencies | 1.4%-8% improvement in productivity 2. 2-5% improvement in Quality | Blueprinting, Devlopment, Testing and UAT -30-36 weeks | API | TCS, TS1,TS2, Mastercom/ VROL, Workflow system | 1, Genpact team will have required level of access to AI Infra for hosting and running AI agents. We will leverage FIS technology stack to develop the solution 2. The solution will leverage API layer mentioned to fetch/ update data with other applications and converned applications support API calls for data transfer. 3. Client SMEs and relrevant knowledgebase will be accessible to Genpact team. 4. Security protocols and access controls will be in place for handling sensitive data. 5. All necessary InfoSec and legal approvals will be secured by the client prior to project execution. |  | 0.046698 | 0.62075 | 0.89384 | 0.99131 | 1.0913 | 1.1126 | 1.1306
AI Agent Software Simulation/ AI coach | Risk | A sandbox environment, where agents can practice virtual call types which will help agents with handling various types of queries related to fraud and dispute. Agents can be coached on both inbound & outbound calls and back office processing and putting the right emphasis on regulatory scripts, verification process, investigation and account actions. | Digital Efficiencies | 1.3-5% improvement in productivity 2. 2-5% improvement in Quality | Blueprinting, Devlopment, Testing and UAT - 6 weeks | No Integrations required | No Integrations required | 1. Security protocols and access controls will be in place for handling sensitive data. 2. All necessary InfoSec and legal approvals will be secured by the client prior to project execution. |  | 0.015566 | 0.20692 | 0.29795 | 0.33044 | 0.36376 | 0.37086 | 0.37686
Nudge Coach | Risk | Agent performance improvement using incremental performance focused daily nudges | Digital Efficiencies | 1.3-5% improvement in productivity 2. 2-5% improvement in Quality | Blueprinting, Devlopment, Testing and UAT - 6 weeks | No Integrations required | No Integrations required | 1. Security protocols and access controls will be in place for handling sensitive data. 2. All necessary InfoSec and legal approvals will be secured by the client prior to project execution. |  | 0.015566 | 0.20692 | 0.29795 | 0.33044 | 0.36376 | 0.37086 | 0.37686
Agentic Service Request Processing (including Automated notes & case summarization) | Back Office /Agenctic AI | Autonomously orchestrates end‑to‑end servicing workflows—covering data capture, intelligent document processing, contextual understanding, and AI‑led decisioningt. It includes GenAI‑powered case summarization and automated notes generation | Digital Efficiencies, Productivity | 1. 40-50% AHT reduction for servicing case handling 2. 10- 15% CX improvement from current baseline | Blueprinting, Development, Testing and UAT - 24 weeks.. This can be delivered in Phases | API | TCS, TS1, TS2, Document Management System, Workflow System | 1. API access to core banking systems for data retrieval 2. Access to historical case data for model training |  | 0.056312 | 0.63884 | 0.91774 | 1.0521 | 1.1856 | 1.2089 | 1.2286
Intelligent Document Extraction & Validation | Back Office /Agenctic AI | The solution automates the extraction and validation of documents received with service request, eliminating manual handling. Verifies authenticity and validity, and matches extracted information against application data | Digital Efficiencies, Productivity | 1 Up to 50% reduction in document validation effort 2. Up to 30% reduction in document validation errors ​ | Blueprinting, Development, Testing and UAT - 16 weeks. This can be delivered in Phases | API | Document Management System, Imaging Platform, TCS, TS1, TS2, Workflow System | 1. Access to document repository and imaging systems 2. Sample document sets for model training 3. Document taxonomy and classification rules from client 4. Integration with existing DMS infrastructure |  | 0.035195 | 0.39927 | 0.57359 | 0.65756 | 0.741 | 0.75557 | 0.76789
Autonomous Data Aggregation & Bureau Updates | Back Office /Agenctic AI | Automated data aggregation from multiple sources for credit bureau reporting and updates. Includes intelligent validation of bureau data, exception identification, and automated submission of updates to credit bureaus | Digital Efficiencies, Productivity, Labor Arbitrage | 1.30-40% faster processing 2. Up to 50% Reduction in duplicate and rework activities | Blueprinting, Development, Testing and UAT - 20 weeks.This can be delivered in Phases | API | TCS, TS1, TS2, Experian/TransUnion/Equifax APIs, Reconciliation System | 1. API connectivity to credit bureau systems 2. Access to account data and transaction history 3. Client approval for automated bureau submissions |  | 0.021117 | 0.23956 | 0.34415 | 0.39453 | 0.4446 | 0.45334 | 0.46074
Card Network Investigation Agent | Back Office /Agenctic AI | Automates intake, evidence analysis, and investigation workflows across network dispute cases, enabling faster, compliant resolution. | Digital Efficiencies, Productivity, Labor Arbitrage | Up to 70% Improvement in Credit Risk exposure | Blueprinting, Development, Testing and UAT - 24 weeks | API | TCS, TS1, TS2, Mastercom, VROL, Workflow System, Document Management System | 1. API access to Visa/Mastercard portals 2. Historical chargeback data for model training 3.Client chargeback rules and decision frameworks |  | 0.017598 | 0.19964 | 0.28679 | 0.32878 | 0.3705 | 0.37778 | 0.38395
Genpact’s Dynamic Workflow Orchestration provides a unified system of engagement to orchestrate complex back‑office cards operations | Back Office | The solution spans the full scope of back‑office processing, including imaging, correspondence processing, and exception handling with automated case creation, tracking, and resolution. It also covers downstream system updates, and proactive customer outreach triggers. | Digital Efficiencies, Productivity | 1. 40-50% AHT reduction in case handling 2. ~ 30% increase in STP for Service Request Processing | Blueprinting, Development, Testing and UAT - 20 weeks . This can be delivered in Phases | API/Native | TCS, TS1, TS2, Workflow System, Communication Platform, GL System | 1. Access to workflow rules and routing logic 2. Integration with communication platforms 3. Real-time queue monitoring capabilities 4. Escalation matrix and SLA definitions from client |  | 0.028156 | 0.31942 | 0.45887 | 0.52605 | 0.5928 | 0.60445 | 0.61431
Gen AI-powered Customer Email & Correspondence | Back Office/Gen AI | GenAI-powered solution for automated correspondence processing and response generation. Includes intelligent email classification, template selection, personalized response drafting, and compliance-checked customer communications | Digital Efficiencies, Productivity, Labor Arbitrage | 1. Up to 50% reduction in response errors (policy, data, or tone deviations 2. 15-20% improvement in customer satisfaction | Blueprinting, Development, Testing and UAT - 16 weeks | API | Email Platform, TCS, TS1, TS2, Document Management System, | 1. Access to correspondence templates and brand guidelines 2. Historical email corpus for model fine-tuning 3. Integration with existing email/messaging platforms |  | 0.014078 | 0.15971 | 0.22944 | 0.26302 | 0.2964 | 0.30223 | 0.30716
Dynamic Volume Forecasting | Back Office/Predictuve | Intelligent forecasting of back‑office workload volumes to enable proactive resource planning and dynamic workload balancing across multiple work and request streams. | Digital Efficiencies, Productivity, Labor Arbitrage | 1. 20-30% improvement in workforce utilization | Blueprinting, Development, Testing and UAT - 12 weeks | API | WFM System, TCS, Workflow System, | 1. Historical volume data 2. Business calendar and seasonal patterns 3. Integration with queue management systems |  | 0.017598 | 0.19964 | 0.28679 | 0.32878 | 0.3705 | 0.37778 | 0.38395
Real time Operational Analytics | Back Office | Real‑time operational analytics provide continuous visibility into back‑office performance across volumes, queues, SLAs, and exceptions—enabling proactive decision‑making and tighter operational control. | Digital Efficiencies, Productivity | 1. 20-30% faster issue identification and resolution 2. 20-30% reduction in SLA breaches | Blueprinting, Development, Testing and UAT - 12 weeks | API | TCS, TS1, TS2, Reporting/BI Tools, WFM System, | 1. Access to operational data sources and APIs 2. KPI definitions and SLA thresholds from client |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Automated Mailbox Management | Back Office/RPA | Automated triage, classification, prioritization, and routing of inbound communications, including customer inquiries, and servicing requests. | Digital Efficiencies, Productivity, Labor Arbitrage | 1. 40-50% reduction in mailbox processing time 2. 30-40% reduction in misrouted items | Blueprinting, Development, Testing and UAT - 12 weeks | API | Email Platform, Document Management System, Workflow System, TCS | 1. Access to mailbox systems and email platforms 2. Classification taxonomy and routing rules 3. Priority definitions and SLA requirements |  | 0.010559 | 0.11978 | 0.17208 | 0.19727 | 0.2223 | 0.22667 | 0.23037
AI Agent Software Simulation/ AI coach | Back Office/AI | A sandbox environment that enables agents to practice and simulate different back‑office request types | Digital Efficiencies, Productivity | 1. 2-3% improvement in productivity 2. 2-5% improvement in Quality | Blueprinting, Development, Testing and UAT - 6 -8 weeks | No Integrations required | No Integrations required | Process documentation and SOPs |  | 0.0035195 | 0.039927 | 0.057359 | 0.065756 | 0.0741 | 0.075557 | 0.076789
Nudge Coach | Back Office/AI | Agent performance improvement using incremental performance focused daily nudges | Productivity | 1. 2-3% improvement in productivity 2. 2-5% improvement in Quality | Blueprinting, Development, Testing and UAT - 6 -8 weeks | No Integrations required | No Integrations required |  |  | 0.0035195 | 0.039927 | 0.057359 | 0.065756 | 0.0741 | 0.075557 | 0.076789
5.4 Vendor Funded Technology Costs
Summarize what you are willing to fund with regard to this Technology Transition from the Legacy TSYS technology stack to the FIS Technology stack. Please provide a cost breakdown of this effort. Add additional rows as needed.
Cost Types | Total to Be Funded by the Vendor ($M)
NA
NA
Total
5.5 Technology Responsibility Matrix
Populate a RACI of what TSYS/FIS will be responsible for and what you will be responsible for. Please augment the table as you see fit.
Activity | TSYS/FIS | Insert Vendor Name | [Insert Vendor Name]
Strategy & Planning
Business Requirements Definition | R/A | C
Technical Requirements Definition | R/A | C
Architecture Design | C | R/A
Migration Strategy | C | R/A
Implementation Roadmap | C | R/A
Environment Planning | C | R/A
Design
Application Configuration Design | C | R/A
Integration Design | C | R/A
Data Mapping Design | C | R/A
Security and Controls Design | C | R/A
Test Strategy Development | C | R/A
Build & Configuration
Platform configuration | C | R/A
Integration Development | C | R/A
API Setup | C | R/A
Workflow Configuration | C | R/A
Automation Setup | C | R/A
Reporting Configuration | C | R/A
Testing | C | R/A
Unit Testing | C | R/A
System Integration Testing (SIT) | C | R/A
Data Validation | C | R/A
User Acceptance Testing (UAT) | R/A | C
Performance Testing | C | R/A
Security Testing | R/A | C
Migration & Cutover
Data Migration Execution | C | R/A
Parallel Run | C | R/A
Cutover Planning | C | R/A
Production Deployment | C | R/A
Go-Live Support
Stabilization
Hypercare Support | C | R/A
Incident Management | C | R/A
Defect Remediation | C | R/A
Performance Monitoring | C | R/A
Ongoing Managed Services
Incident Management | C | R/A
Project Management | C | R/A
Dependendency Management | C | R/A
Change Management | C | R/A
Release Management | C | R/A
Enhancement Management | C | R/A
Continuous Improvement | C | R/A
Platform Support | C | R/A

## 6.0 Pricing
6.0 Pricing
All pricing in USD, exclusive of taxes. Four sections: (1) rate card for recurring operational costs by service and geography; (2) Fixed Fee Pricing; (3) One-time transition, Upfront Investments and Implementation costs; (4) Pricing Assumptions; (5) Productivity Assumptions. State all assumptions clearly. Itemize by service and geography throughout.
6.1 Rate Card — Recurring Operations
Provide your rate card for all recurring operational services. Price each sub-service by geography. Assume the unit is in hours. Where you cannot price a line item, state 'Included' or 'N/A' and explain in Assumptions.
Service | Sub Service | North America — US | North America — Canada | North America — PHP | EMEA — UK | EMEA — Netherlands | EMEA — Germany | India
|  | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($)
Tier 1 Customer Service | IVR | 48.4804 | 0 | 0 | 0 | 0 | 0 | 0
| Multilingual | 48.4804 | 48.4804 | 0 | 42.0705 | 49.3998 | 42.7326 | 0
| Live Agent | 48.4804 | 0 | 16.6782 | 42.0705 | 49.3998 | 42.7326 | 0
| Loyalty | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 0
| Lost/Stolen | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 0
| After hours | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 0
Tier 2 Risk Mitigation | Fraud Detection | 48.4804 | 0 | 16.4673 | 42.0705 | 49.3998 | 42.7326 | 0
| Fraud Investigation | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 0
| Fraud Strategy | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 0
| Fraud Consulting | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 0
| Collections | 48.4804 | 0 | 0 | 0 | 0 | 0 | 0
| Skip Tracing | 48.4804 | 0 | 0 | 0 | 0 | 0 | 0
| Disputes & Chargebacks | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 0
| Risk Call Center | 48.4804 | 0 | 16.4673 | 42.0705 | 49.3998 | 42.7326 | 0
| Credit | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 0
Back Office | Imaging | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 12.4946
| Copy Requests | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 12.4946
| Correspondence | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 12.4946
| Application Processing | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 12.9211
| Credit Bureau Updates | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 12.9211
| Returned Mail | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 12.9211
| Card Destruction | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 12.4946
| Account Maintenance | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 12.9211
| Accounting & Settlement | 48.4804 | 0 | 0 | 42.0705 | 49.3998 | 42.7326 | 12.9211
6.2 Annual Cost Escalation by Country
State your assumed annual COLA percentage by country. Must be consistent with your rate card and fixed fee submissions.
Annual COLA Assumption | %
United States | 3%
Canada | 3%
Philippines | 5%
United Kingdom | 3%
Netherlands | 3%
Germany | 3%
India | 5%
6.3 Fixed Fee Pricing
Provide quarterly fixed fees for front office, back office, and vendor-funded technology credits over the contract term. Must reconcile to Tab 4.0 and Section 6.1.
Service | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Year 7
($M) | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Fixed Fee — For Front Office Operations | 38.3078 | 40.4682 | 40.9235 | 39.4086 | 40.268 | 26.8261 | 19.1915 | 17.0177 | 12.604 | 12.1701 | 11.6874 | 11.2855 | 11.0282 | 10.6591 | 9.8864 | 9.8864 | 9.0981 | 9.0981 | 8.8239 | 8.8239 | 8.7888 | 8.7888 | 8.7888 | 8.743 | 8.6197 | 8.6197 | 8.6197 | 8.6197
Fixed Fee — For Back Office Operations | 7.1305 | 6.966 | 6.76 | 6.2049 | 5.7224 | 3.9821 | 2.9132 | 2.6088 | 1.9156 | 1.8588 | 1.7874 | 1.7321 | 1.692 | 1.6408 | 1.4694 | 1.4694 | 1.3478 | 1.3478 | 1.3081 | 1.3081 | 1.3024 | 1.3024 | 1.3024 | 1.2958 | 1.2774 | 1.2774 | 1.2774 | 1.2774
Vendor-Funded Technology Investment / Implementation Credit | -3.4661 | -3.4661 | -3.4661 | -3.4661 | -2.3653 | -2.3653 | -2.3653 | -2.3653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4 One-Time Transition, Upfront Investments & Implementation Costs
List all one-time costs. Itemize by cost type and geography. Clearly distinguish vendor-funded investment from costs borne by FIS.
Cost Type | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Year 7
Examples Below | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Set up Cost | 1.1304 | 1.4186 | 1.4186 | 1.4186 | 1.1679 | 1.1679 | 1.1679 | 0.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rebadging / HR Transition Costs - Onboarding | 2.6827 | 0 | 0 | 0 | 4.1009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technology Overlay Integration | 0 | 0 | 2.614 | 2.614 | 6.0992 | 6.0992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technology Overlay Licensing | 0 | 0 | 1.0576 | 1.0576 | 0.93146 | 0.93146 | 0.93146 | 0.93146 | 0.78281 | 0.78281 | 0.78281 | 0.78281 | 0.74565 | 0.74565 | 0.74565 | 0.74565 | 0.40999 | 0.40999 | 0.40999 | 0.40999 | 0.36915 | 0.36915 | 0.36915 | 0.36915 | 0.33199 | 0.33199 | 0.33199 | 0.33199
Technology Migration | 2.0738 | 2.0738 | 2.0738 | 2.0738 | 2.3938 | 2.3938 | 2.3938 | 2.3938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training | 1.1052 | 1.7857 | 1.5077 | 1.3553 | 2.0711 | 0.050955 | 0.31613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Professional Services | 1.0682 | 1.0682 | 0 | 0 | 0.15926 | 0.15926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Run Charges | 2.3754 | 2.3754 | 2.3754 | 2.3754 | 0.66962 | 0.66962 | 0.66962 | 0.66962 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754 | 0.26754
Dual Run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up front Investments | -3.4661 | -3.4661 | -3.4661 | -3.4661 | -2.3653 | -2.3653 | -2.3653 | -2.3653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
In Year Discounts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.5 Upfront Investment Conditions | bar: Year 1 Q1 to Year 5 Q4
For each condition, confirm whether it applies to your proposed investment and provide the required threshold or value.
Conditions for receiving one-time vendor cash payment | Year 1 Q1: Is this a condition (Y/N); Year 1 Q2: Required value
Is there a minimum volume requirement for NA scope of work, if yes provide % of total volume | Year 1 Q1: Yes; Year 1 Q2: TBD
Is there a minimum volume requirement for EMEA scope of work, if yes provide % of total volume | Year 1 Q2: TBD
Is partial or complete rebadging (specified in section 3) a pre condition to this upfront investment? | Year 1 Q1: No; Year 1 Q2: TBD
Minimum contract duration, if yes provide number of years | Year 1 Q1: Yes; Year 1 Q2: 7
Other: <pls add additional rows as necessary>
6.6 Pricing Assumptions | bar: Year 1 Q1 to Year 5 Q3
List all assumptions underpinning your pricing across all three sections above. Include: FTE volume assumptions, indexation methodology, how you have structured fixed vs. variable components, your fixed fee breakdown (front-office vs. back-office), any vendor-funded technology investment or implementation credit, and any deal sweeteners, transition credits, or gain-share mechanisms proposed.
# | Year 1 Q1: Assumptions
1 | Year 1 Q1: Genpact assumes that Rebadge FTEs include all the support-supervision roles or bench required to run the operations independently. Hence, no additional role or headcount has been included by Genpact in solution & commercials. Rate cards are basis this assumption.
2 | Year 1 Q1: Rebadged resource decoupling timeline: ~90% for US-UK and ~70% for Canada-Netherlands-Germany offshoring to the Philippines and India by month 12 from go-live. Any change or delay in same due to any Client dependency or local laws would lead to change in charges.
3 | Year 1 Q1: Committed productivity of ~68% over 7 years deal term
4 | Year 1 Q1: FIS – TMS current Attrition / month: US Front Office: 4%; US Back office: 2.5%; Canada: 2%; UK: 1.5%; GE: 1.5%; NL: 0%
5 | Year 1 Q1: Genpact charges are COLA exclusive. Charges will be adjusted for indexation from the first anniversary of the contract signature date and thereafter each anniversary, basis above mentioned COLA %
6 | Year 1 Q1: Payment terms: 75 days with 15 days of advance billing.
7 | Year 1 Q1: Genpact has considered rebadging of Client's employees. Genpact will perform due diligence to verify the accuracy and completeness of Client’s information on which the Services and the Charges were developed, including the assumptions,the actual costs of the Transitioned (rebadged) Employees, FTEs charges, and true up the charges basis due diligence results.
8 | Year 1 Q1: Up to the talent transfer closing date (i.e. transfer to Genpact), all liabilities, including any severance or related costs owed to rebadged employees shall be borne by FIS. Post transfer to Genpact, Rebadge resources severance cost will be borne by Genpact, for the tenure spent at Genpact only. FIS to cover severance for FIS tenure as per precedent.
9 | Year 1 Q1: Rebadge resources (except in Philippines) will continue to operate from FIS locations and will continue to use FIS laptops & office network. Such expenses will be handled in pass-through mode. In Philippines, Rebadge resources will work from Genpact facility.
10 | Year 1 Q1: Genpact will baseline the volumes and AHT for 3 months before committing on the SLAs and AHT targets.
11 | Year 1 Q1: The rates/ charges provided are foconsidering a deal term of 7 years, including transition period, for the scope and information as provided in the RFP. These rates are valid for a period of 90 days from the date of submission (27th March). If there is a further delay to closure of the contract or in case in case of any changes to information received (including through the due diligence process), there might be an impact to the charges.
12 | Year 1 Q1: Both Pricing and Invoicing remain fixed in USD.
13 | Year 1 Q1: Below annual Productive hours have been considered per FTE : i)US & Canada- 1674 ii) UK- 1656 iii) Netherlands- 1530 iv) Germany- 1530 v) Philippines- 1573 vi) India- 1873
14 | Year 1 Q1: The Services will be in the following languages to be delivered out of the below Genpact delivery centers. Any change in the language/delivery location or the split of resources across the different languages/delivery locations will have an impact on the charges. (i) Pune, India - English. (ii) Alabang, Philippines - English. (iii) US, Columbus- Spanish & English (iv) Canada- French & English (v) Germany- German & English (vi) Netherlands- Dutch & English
15 | Year 1 Q1: All committed productivity is subject to: (i) Timely completion of transition, transformation (ii) Timely implementation of the proposed tools and migration (iii) Client dependencies Any delay or change in the above may lead to a change in the committed productivity and charges
16 | Year 1 Q1: We do not seek to be compensated for the loss of profit or margin. Our termination fees are designed to mitigate costs that cannot be recovered. These termination charges typically include: 1. Termination fee for employee costs such as severance/redeployment of displaced colleagues 2. Unamortized/deferred charges beyond completion of service 3. Any deal investments 4. Any third party breakage fees and lease termination penalties Notice period of 120 days to be provided in case of termination event
17 | Year 1 Q1: Pass through charges like PSTN, postage, courier and specific travel undertaken at customer's request, etc will be recovered on actual. A list of such charges will be identified and agreed with customer. Currently, we have not provided the estimate of pass through charges as the same would be recovered on actual & on monthly basis.
18 | Year 1 Q1: Current solution asumes 50% Work-from-home across locations. All FTEs will be laptop enabled, catering for a work-from-home BCP solution if applicable. If there is a specific requirement of Hot/Cold seats BCP solution, additional charges may be applicable.
19 | Year 1 Q1: Contract term of 7 years has been assumed to begin from Oct'26 (from 1st Rebadge GoLive). Commercials are basis the same.
20 | Year 1 Q1: Rates/ Charges do not include taxes applicable to the client due to this outsourcing agreement. If Genpact is required to pay any federal, state, county or local service or value added tax (VAT) or sales, use, gross receipts, excise, withholding, consumption, or any other Governmental Entity taxes assessed on the Services provided, such taxes (along with any applicable surcharge thereon), including any gross-up on withholding tax, will be billed to and paid by the client upon presentation of details that substantiate the amount of the taxes.
21 | Year 1 Q1: Overtime and night shifts will be at premium.
22 | Year 1 Q1: 1. Genpact is investing ~$23M into this partnership with specific considerations and such investment is therefore subject to change if there is a movement in scope/deal value. 2. This investment is to enable the implementation of the program to yield an optimal financial outcome. 3. This has been structured such that it supports FIS to cover the initial costs in the first 2 years 4. Unlike other charges, the deal investment is not tied to Genpact’s performance obligation and will therefore be treated outside of the termination conditions. 5. In case of all termination events, Genpact shall recover full deal investment (to be pro-rated in case of partial termination) paid by Genpact to Client.
23 | Year 1 Q1: It is assumed that at the time of expiry/ termination, the rebadged employees will be transferred to the Client or the successive supplier and the corresponding cost impact as mutually agreed by the Parties shall be borne by the Client.
24 | Year 1 Q1: Retention Bonus is considered @ 2 month base salary for 25% resources. A change in the same will lead to a change in prices.
25 | bar: Year 1 Q3 to Year 5 Q3
26 | bar: Year 1 Q3 to Year 5 Q3
27 | bar: Year 1 Q3 to Year 5 Q3
Section 6.7 — 5-Year Financial Summary | bar: Year 1 Q1 to Year 5 Q3
Summarize the total cost of the proposed engagement over the contract term. All figures in USD millions. This table will be used to calculate Total Contract Value and net savings versus FIS's cost baseline. Figures must be consistent with pricing submitted in Sections 6.1–6.3 above. Efficiency savings figures in this table must reconcile directly to commitments stated in Tab 5.0 Technology Solution. Any discrepancy between this table and Tab 5.0 must be explained in Section 6.4 Pricing Assumptions.
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Year 7
Cost Category | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
North America Direct Costs | 31.9828 | 27.7056 | 24.784 | 19.422 | 17.8023 | 14.2518 | 10.4038 | 9.6933 | 8.1265 | 7.823 | 7.4797 | 7.1967 | 7.0152 | 6.7579 | 6.1667 | 6.1667 | 5.6291 | 5.6291 | 5.4347 | 5.4347 | 5.4126 | 5.4126 | 5.4126 | 5.3802 | 5.2953 | 5.2953 | 5.2953 | 5.2953
EMEA Direct Costs | 9.9894 | 16.2625 | 19.4334 | 22.7254 | 25.8228 | 14.1911 | 9.3356 | 7.5679 | 6.3931 | 6.2058 | 5.9952 | 5.8209 | 5.7051 | 5.5419 | 5.1891 | 5.1891 | 4.8168 | 4.8168 | 4.6973 | 4.6973 | 4.6786 | 4.6786 | 4.6786 | 4.6587 | 4.6018 | 4.6018 | 4.6018 | 4.6018
Total Annual Cost ($M) | 41.9722 | 43.9681 | 44.2174 | 42.1473 | 43.6251 | 28.443 | 19.7393 | 17.2612 | 14.5196 | 14.0288 | 13.4749 | 13.0176 | 12.7202 | 12.2998 | 11.3558 | 11.3558 | 10.446 | 10.446 | 10.132 | 10.132 | 10.0912 | 10.0912 | 10.0912 | 10.0389 | 9.8971 | 9.8971 | 9.8971 | 9.8971
Savings (%)

## 7.0 Client Migration
7.0 Client Migration Planning
A de-identified client dataset will be provided alongside this RFP. A migration wave is a defined group of clients that will transition to the new operating model together, with a shared go-live date and dual-run period. (1) Using the supplemental data provided, please architect waves of clients/queues/locations/ regions and articulate the rationale. (2) Use the Wave Summary below to plot your wave against time. (3) Define a RACI for the Client Migration efforts.
7.1 Client Migration Wave Design
Part 1 — Wave Composition: For each wave, list which client cohorts are included, explaining what criteria drove the grouping; for all clients, specify which client is mapped to each wave. FIS has intentionally not prescribed a wave structure or grouping methodology. We expect vendors to analyze the client dataset provided and propose the wave design they believe is most operationally sound for an engagement of this complexity. There is no correct number of waves. Responses that demonstrate genuine analytical thinking about client risk, regulatory complexity, volume sequencing, and transition readiness will be evaluated more favorably than generic frameworks.
Wave # | Client Name | Wave Assignment Rationale | Key Migration Risks & Mitigations | [Add additional columns as desired]
Wave 1 | Client X | Vendor to provide rationale | Vendor to identify | Vendor to identify
Wave 1 | 40 Clients serving from Columbus region | Phased and Risk-Balanced Approach: By sequencing NA (Columbus, Canada, PHP) first, we adopt a phased execution strategy - • Lower Regulatory and Complexity Risks, compared to Europe • Stabilize high-confidence regions early • Incorporate learnings and best practices from similar previous engagements • Genpact’s approach in Canada would be to rehire employees following a clear and compliant separation from FIS. • This structured rehire model ensures full adherence to local labor and employment regulations while enabling continuity of services, retention of critical skills, and minimal disruption to ongoing operations • PHP - Rebadging in the Philippines ensures uninterrupted delivery by retaining experienced, client‑embedded talent in a proven, cost‑efficient location already supporting Gamma 7 operations The UK is partially aligned through Wave 1, targeting segments with comparable readiness and risk profiles. • UK Wave 1 includes roles with minimal regulatory dependency and no requirement for extended consultation, allowing alignment with the NA timeline and early stabilization of critical operations. | Risk: Change communication and logistics - Delayed/Inadequate communication due to multi country engagement Mitigation: • Drive region‑specific communication aligned with the Transition Plan, supported by a detailed change communication roadmap initiated • Open lines of communication – multi level governance Risk - Attrition and knowledge loss - Low offer acceptance rate / High rate of Offer drops Mitigation - • Ring fence key resources early – use retention tools • Proactive contingency hiring to manage any gaps
13 clients serving from Canada region
2 clients serving from PHP
3 clients serving from Milton Keynes
Wave 2 | 3 clients serving from Milton Keynes | Remaining UK (50%) deferred to Wave 2, which provides a longer runway to address regulatory and complexity‑led dependencies before cutover, reducing execution and compliance risk • UK Wave 2 may include roles subject to formal consultation requirements, increased regulatory dependency, or additional change‑management readiness. • Sequencing these roles in Wave 2 allows sufficient time to complete consultation processes and address employee feedback • Execution of Wave 2 will incorporate learnings from NA and UK Wave 1, enabling a more informed, compliant, and lower‑risk transition while maintaining business continuity. | Risk: Consultation & Regulatory Delays - Extended employee consultation or regulatory requirements may delay rebadging timelines. Mitigation: • Plan consultations early with defined milestones and owners. • Partner with local HR and Legal to meet all statutory obligations. • Reuse proven materials and playbooks from NA and UK Wave 1. Risk: Employee Uncertainty & Attrition (Wave 2) - The execution of rebadging in Wave 1, combined with a time gap of 2 months before Wave 2, may create uncertainty and perceived inequity among remaining employees, reducing engagement and increasing the risk of attrition in critical roles. Mitigation: • Deploy a focused change management and communications plan for Wave 2. • Provide clear, regular updates on timing, rationale, and next steps. • Identify critical roles and implement targeted retention or engagement actions. Risk: Operational Disruption During Rebadging Wave 2 roles may be operationally critical, increasing the risk of service disruption if transitions are poorly sequenced or executed. Mitigation: • Complete role level criticality and dependency assessments ahead of execution. • Establish robust transition and knowledge transfer plans. • Sequence execution to avoid peak operational demand conflicts.
Wave 3 | 2 clients service from Barneveld region | EMEA is intentionally sequenced as the final wave due to its multi‑country regulatory landscape, varying labor laws, and extended consultation requirements. Positioning Europe after NA and UK ensures the rebadging is executed using a fully tested approach, minimizing legal exposure, operational disruption, and employee‑related risks. • Enter Europe with a proven, lower‑risk rebadging model | Risk: Regulatory and compliance gaps due to diverse labor laws, employment regulations, and consultation requirements across multiple European countries. Mitigation: Country-Specific Regulatory Assessment - Engage local legal expertise to validate regulatory interpretations and ensure alignment with jurisdiction‑specific requirements. Identify countries requiring works council or employee representative consultation early in the planning phase. Ensure documentation, contracting, and onboarding fully align with local employment regulations.
2 clients service from Hamburg region
(Add additional rows as desired)
7.2 Migration Wave Migration Plan | [18 empty] | Kiran & Sonal
Part 2 — Wave Timeline: For each wave, state the proposed start date, go-live date, and dual-run duration. Please visually differentiate between the migration and dual run periods, if applicable. FIS has intentionally not prescribed a wave structure or grouping methodology. We expect vendors to analyze the client dataset provided and propose the wave design they believe is most operationally sound for an engagement of this complexity. There is no correct number of waves. Responses that demonstrate genuine analytical thinking about client risk, regulatory complexity, volume sequencing, and transition readiness will be evaluated more favorably than generic frameworks.
Wave | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Wave 1 (Columbus, Canada, PHP and Milton Keynes) | Year 1 Q4: 2026-11-01
Wave 2 (Milton Keynes) | Year 2 Q1: 2027-01-01
Wave 3 (Barneveld, Hamburg) | Year 2 Q2: 2027-06-01
2027-06-01
7.3 Client Migration Responsibility Matrix | bar: Year 1 Q1 to Year 1 Q2
Populate a RACI of what TSYS/FIS will be responsible for and what you will be responsible for; FIS has not pre-populated this RACI. Vendors are expected to propose the full activity list they believe is required to execute a migration of this scale, and to assign responsibility accordingly. Responses should reflect your actual delivery methodology — not a generic RACI template. Activities should cover at minimum: client readiness, knowledge transfer, dual-run management, cutover approval, stabilization, and hypercare exit. Add rows as needed.
Rebadge Activity | Year 1 Q1: TSYS/FIS; Year 1 Q2: Genpact
Assess | bar: Year 1 Q1 to Year 1 Q2
Initiate due diligence | Year 1 Q1: A; Year 1 Q2: A/R
Define scope | Year 1 Q1: R; Year 1 Q2: A/R
Map existing principles and benefits | Year 1 Q1: A; Year 1 Q2: R/A
Business case and risk mitigation | Year 1 Q1: C; Year 1 Q2: A/R
Project charter / flying formation and establish governance model | Year 1 Q1: C; Year 1 Q2: A/R
Identify critical employee list | bar: Year 1 Q1 to Year 1 Q2
Design | bar: Year 1 Q1 to Year 1 Q2
Completion of details: Due diligence | Year 1 Q1: C; Year 1 Q2: A/R
Project team and plan setup | Year 1 Q1: I; Year 1 Q2: A/R
Define the communication calendar & key dates for the consultative process | Year 1 Q1: C; Year 1 Q2: A/R
HR due diligence / benefits harmonization / retention strategy | Year 1 Q1: I; Year 1 Q2: A/R
Complete as-is process documentation assessment and agree on the approach to close the gaps | Year 1 Q1: A; Year 1 Q2: A/R
Future state control ownership and framework design (retained + delivery center) | bar: Year 1 Q1 to Year 1 Q2
Execute | bar: Year 1 Q1 to Year 1 Q2
Plan communication and Genpact introduction | Year 1 Q1: R; Year 1 Q2: A/R
Consultation process / employee communication | Year 1 Q1: C; Year 1 Q2: A/R
Create communication and branding collaterals | Year 1 Q1: A/R; Year 1 Q2: A/R
Notification letters / offer letters release | Year 1 Q1: R/C; Year 1 Q2: A/R
Conduct training sessions for retained teams per change and comms. plan (new ways of working) | Year 1 Q1: A/R; Year 1 Q2: C/I
System access and credential setup | Year 1 Q1: A/R; Year 1 Q2: C
Complete process training for backfill and bench resources as per plan | Year 1 Q1: R; Year 1 Q2: A/R
As-is process documentation assessment | Year 1 Q1: C; Year 1 Q2: A/R
Cutover planning and execution | Year 1 Q1: C/I; Year 1 Q2: R/A
7.4 Transformation Assumptions | bar: Year 1 Q1 to Year 2 Q1
At a per client level, what is the commitment from the vendor on offshore to onshore mix, consequent labor arbitrage %, cost reduction from AI & Digital Overlays, cost reduction from Productivity gains
Client Name | Year 1 Q1: Offshore to Onshore Mix Day 1; Year 1 Q2: Offshore to Onshore Mix- End State; Year 1 Q3: Consequent Labor Arbitrage %; Year 1 Q4: Cost Reduction from AI & Digital Overlays %; Year 2 Q1: Cost Reduction from Productivity Gains %; Year 2 Q2: Commitment to Certainty of Cost Savings as a %
US & Canada Clients Clients | Year 1 Q1: 100%; Year 1 Q2: 90%; Year 1 Q3: 67.68%; Year 1 Q4: 39.51%; Year 2 Q1: Vendor to provide; Year 2 Q2: TBD
Netherlands Clients | Year 1 Q1: 100%; Year 1 Q2: 70%; Year 1 Q3: 65.28%; Year 1 Q4: 27.91%; Year 2 Q2: TBD
Germany Clients | Year 1 Q1: 100%; Year 1 Q2: 70%; Year 1 Q3: 59.87%; Year 1 Q4: 29.1%; Year 2 Q2: TBD
United Kingdom Clients | Year 1 Q1: 100%; Year 1 Q2: 70%; Year 1 Q3: 59.87%; Year 1 Q4: 38.02%; Year 2 Q2: TBD
Philippines Clients | Year 1 Q1: 0%; Year 1 Q2: 0%; Year 1 Q3: 0%; Year 1 Q4: 51.97%; Year 2 Q2: TBD
Labour Arbitrage is the differential between onshore and offshore rates
Cost Reduction from AI & Digital Overlays %+Cost Reduction from Productivity Gains % : are represented together and are the savings % post right shoring

## 8.0 Regulatory Compliance
8.0 Regulatory Compliance
For each requirement listed in Column C, provide your response in Column D. Responses should be specific to this engagement and the regulatory environments in scope. Where certifications or formal frameworks apply, state them.
8.1 Transformation Assumptions
Regulatory Area | Specific Requirement | Vendor Response — How Your Solution Meets This Requirement
4th Party Outsourcing | Disclose all sub-contractors by name, location, and scope. Confirm SLA flow-down and FIS audit rights over all 4th parties. | At this time, we do not envision any subcontractors to be leveraged for the delivery of services.
4th Party Outsourcing | Describe your internal governance model for monitoring sub-contractor performance and compliance. | At this time, we do not envision any subcontractors to be leveraged for the delivery of services.
Offshoring & Nearshoring | Confirm cardholder data will not leave approved jurisdictions without explicit client consent. Describe data residency controls. | Genpact intends to be compliant with any prevaling regulations as applicable. We will work with you to determine the specifics.
Offshoring & Nearshoring | Describe the regulatory notification process before offshoring commences (e.g. FCA Principal 11 notification — UK; WARN Act — US). Confirm who is responsible for filings. | Genpact intends to be compliant with any prevaling regulations as applicable. We will work with you to determine the specifics.
Offshoring & Nearshoring | Describe your approach to clients with explicit offshore restrictions in their current TMS contracts. | Appraoch is being shared in the operating model section of the solution presentation.
Customer PII, GDPR & Privacy | GDPR — confirm DPA agreements, data processor obligations, cross-border transfer mechanisms, and breach notification procedures (including SLA to notify FIS). | Genpact intends to be compliant with any prevaling regulations as applicable. We will work with you to determine the specifics.
Customer PII, GDPR & Privacy | US cardholder data — confirm CCPA compliance and your approach to state-level privacy law variation. | Genpact applies a global approach in ensuring compliance with specific data protection laws, including for example EU, US (various states), Canada, Australia, Philippines, Brazil, South Africa, China. Genpact Global Legal & Compliance team identifies laws and regulations that are applicable to Genpact businesses, functions and operational teams across the relevant regions. Genpact assesses and complies with laws applicable to it in the operation and management of its business. With respect to our clients’ operations, Genpact relies on the client identifying laws and regulations that apply to the client and the specific services to be performed by Genpact. Any operational requirements necessary for the operations to comply with applicable laws are written into the standard operating procedures that are approved by the client, and Genpact then performs services to the standards and in the manner set out in the standard operating procedures.
Customer PII, GDPR & Privacy | PCI DSS — confirm current certification level, scope, and most recent assessment date. | Genpact does not undergo PCI DSS certification at an enterprise level. PCI certification is maintained for specific business accounts/clients where Genpact is exposed to card data and is contractually required to store, process, and transmit credit card data in compliance with PCI DSS requirements, including for specific processes conducted at clients’ request and expense. For PCI DSS certified locations, the certification scope includes physical, network, and logical controls aligned to PCI DSS v4. 0 standards.
InfoSec & Data Governance | Confirm FIS retains full ownership and portability of all data at all times. Describe the mechanism for full data extraction upon contract exit. | Genpact recommends transferring the data back to the client before deletion as part of the contract-termination process. Data deletion (including backups) is governed by the Data Retention and Disposal Policy and is executed after approval from authorized signatories, with disposal logs maintained. Exit assistance is coordinated with Legal by confirming Exit Assistance provisions in the MSA/SOW, discussing and drafting the required Change Order documentation, planning drafting/review/approval/sign-off timelines, reviewing changes post-disengagement, obtaining internal approvals, and creating the Termination Process flow document with cross-functional inputs.
InfoSec & Data Governance | Confirm logical and/or physical segregation of cardholder data across different FIS clients. | Genpact intends to be compliant with all the protocols that FIS/TSYS require as part of service delivery. We will work with you to determine the specifics.
InfoSec & Data Governance | Describe security controls for remote/WFH agents handling cardholder data (screen capture, device management, network security, print restrictions). | Screen capture controls: Screen printing is blocked, and screen capture is disabled for remote/WFH operations. Device management and endpoint controls: Mobile access to corporate networks, data, applications, and systems follows documented policies, with Mobile Device Management and Data Leak Prevention controls. Endpoints use encrypted laptop drives, USB ports disabled by default (enabled only with business justification and approval), DLP monitoring for storage-media events, and mobile restrictions that block copy-paste and discourage saving data to local phone storage. Network security and remote access controls: Remote access uses enhanced VPN, firewall controls, and DLP protections for WFH. Network entry points are protected by IDS/IPS and stateful firewalls, and access is allowed only from PCI-certified, authorized devices. Print restrictions and data handling: Printing is restricted to protect data confidentiality. Only client VDI access is enabled from the endpoint, and client data is not expected to be stored in Genpact’s environment; access occurs within a client-managed VDI. Cardholder-data protection: Card data in Genpact’s custody is encrypted per business, regulatory, and contractual requirements.
Responsibility for Penalties | Who bears liability for regulatory fines resulting from vendor non-compliance? Describe indemnity and remediation framework for client disputes arising from vendor error. | All matters relating to regulatory fines and indemnification shall be governed by and subject to the terms and conditions of the existing Master Services Agreement between the parties.
Financial Services — NA | CFPB — describe your compliance program and oversight model for collections, disputes, and customer service operations. | Genpact is a first party provider and relies on clients to have controls to adhere to CFPB rules such as Reg F for collections.
Financial Services — NA | FDCPA / TCPA — describe compliance approach for collections operations in the United States. | As a first party provider, Genpact work off client systems and platforms and operates within the guidelines of client SOP's and rely on the client to have controls around outbound campaigns that are aligned with the TCPA. We can work with clients to help build systemic controls for these regulations. On the backend, Genpact maintains an internal QA team that reviews and scores calls on compliance related items such as updating DNC and C&D correctly and reading disclosure as appropriate and correctly. New hire training covers both FDCPA and TCPA and we conduct role plays and/or simulations where collectors have to practice skills and compliance tasks.
Financial Services — EMEA | FCA regulated activities — describe your compliance approach for UK-regulated cardholder servicing including complaint handling. | Genpact does not hold the relevant permissions or licenses for cardholder servicing. Based on our preliminary analysis, the services to be outsourced to Genpact do not constitute payment services and does not require Genpact to hold payment services or other financial services authorizations. In this kind of scenarios, Genpact assesses and complies with laws applicable to it in the operation and management of its business. With respect to our clients’ operations, Genpact relies on the client identifying laws and regulations that apply to the client and the specific services to be performed by Genpact. Any operational requirements necessary for the operations to comply with applicable laws are written into the standard operating procedures (SOPs) approved by the client, and Genpact performs the services to the standards and in the manner set out in those SOPs. A thorough end-to-end regulatory assessment for each market will be needed and will be conducted jointly by FIS and Genpact, taking into account all details of each process included in the scope.
Financial Services — EMEA | Germany (BaFin) and Netherlands (AFM/DNB) — describe relevant considerations for Hamburg and Barneveld operations. | Based on our preliminary analysis, the services to be outsourced to Genpact do not constitute payment services under PSD2 and does not require Genpact to hold payment services or other financial services authorizations. In this kind of scenarios, Genpact assesses and complies with laws applicable to it in the operation and management of its business. With respect to our clients’ operations, Genpact relies on the client identifying laws and regulations that apply to the client and the specific services to be performed by Genpact. Any operational requirements necessary for the operations to comply with applicable laws are written into the standard operating procedures (SOPs) approved by the client, and Genpact performs the services to the standards and in the manner set out in those SOPs. A thorough end-to-end regulatory assessment for each market will be needed and will be conducted jointly by FIS and Genpact, taking into account all details of each process included in the scope.
(Add any additional regulatory area) | Add any further regulatory requirements, jurisdictional constraints, or compliance considerations relevant to your proposed delivery model that are not covered above. | In addition to the regulatory requirements outlined above, we recognize that a multi-location delivery model may be subject to evolving regulatory expectations, supervisory guidance, and local compliance obligations. The same can be discussed and agreed mutually with FIS.

## 9.0 Client EfficiencyAssumption
9.0 Client Efficiency Assumptions
9.1 Transformation Assumptions
At a per client level, what is the commitment from the vendor on offshore to onshore mix, consequent labor arbitrage %, cost reduction from AI & Digital Overlays, cost reduction from Productivity gains
Client Name | Offshore to Onshore Mix Day 1 | Offshore to Onshore Mix- End State | Consequent Labor Arbitrage % | Cost Reduction from AI & Digital Overlays % | Cost Reduction from Productivity Gains % | Commitment to Certainty of Cost Savings as a %
US & Canada Clients Clients | 100% | 90% | 67.68% | 39.51% | Vendor to provide | TBD
Netherlands Clients | 100% | 70% | 65.28% | 27.91% |  | TBD
Germany Clients | 100% | 70% | 59.87% | 29.1% |  | TBD
United Kingdom Clients | 100% | 70% | 59.87% | 38.02% |  | TBD
Philippines Clients | 0% | 0% | 0% | 51.97% |  | TBD
Labour Arbitrage is the differential between onshore and offshore rates
Cost Reduction from AI & Digital Overlays %+Cost Reduction from Productivity Gains % : are represented together and are the savings % post right shoring