## 9.0 Client EfficiencyAssump (2)
9.0 Client Efficiency Assumptions
9.1 Transformation Assumptions
At a per client level, what is the commitment from the vendor on offshore to onshore mix, consequent labor arbitrage %, cost reduction from AI & Digital Overlays, cost reduction from Productivity gains
Client Name | Offshore to Onshore Mix | Consequent Labor Arbitrage % | Cost Reduction from AI & Digital Overlays % | Cost Reduction from Productivity Gains % | Commitment to Certainty of Cost Savings as a %
US & Canada Clients Clients | 95:5 | 45% | 19.3% | 11.7% | 39.67%
Netherlands Clients | 95:5 | 5% | 19.3% | 11.7% | 39.67%
Germany Clients | 95:5 | 5% | 19.3% | 11.7% | 39.67%
United Kingdom Clients | 95:5 | 5% | 19.3% | 11.7% | 39.67%
Philippines Clients | 100:0 | 45% | 19.3% | 11.7% | 39.67%

## 1.0 Table of Contents
Response Workbook
TMS Managed Services — RFP Vendor Response Template
Complete all tabs in this workbook. Click a section name below to navigate directly to that tab.
# | Section | Description
1.0 | Table of Contents | Navigation and workbook overview
2.0 | Industry Experience | Organizational track record, workforce, and credentials
3.0 | Relevant Experience | Case studies and client references
4.0 | Workforce & Delivery | Service coverage, languages, sites, workforce migration, and offshore phasing
5.0 | Technology Solution | Technology mapping, governance commitments, AI overlays, and efficiency plan
6.0 | Pricing | Rate card, professional services, one-time costs, and pricing assumptions
7.0 | Client Migration | Client-level migration plan and wave sequencing
8.0 | Regulatory Compliance | Regulatory, compliance, and data governance commitments
9.0 | Client EfficiencyAssumption | commitment from the vendor on offshore to onshore mix, consequent labor arbitrage %, cost reduction from AI & Digital Overlays, cost reduction from Productivity gains

## 2.0 Industry Experience
2.0 Industry Experience
Complete Column D for every row. For rows asking for years of experience, enter the number of years and include a brief note on scope or relevant clients. For all other rows, provide a written response. Specific, evidence-based answers are expected.
2.1 — Industry Track Record
Complete Column D for every row. For rows asking for years of experience, enter the number of years and include a brief note on scope or relevant clients. For all other rows, provide a written response. Specific, evidence-based answers are expected.
Area of Experience | What We Are Asking | Vendor Response
Track Record — Financial Services Issuer Services | Describe your organization's overall track record serving card-issuing financial institutions. Include years in market, number of active issuer clients, approximate ACV managed, and any notable performance milestones. | Sutherland has been a dedicated partner to card-issuing financial institutions for over 19 years, serving debit, credit, and prepaid issuers across Tier-1 banks, specialized card issuers, NBFCs, and fintechs. Today, we support more than 25 active issuer clients globally including 3 of the top 5 card issuers globally representing approximately 70% of issuance volume across our portfolio. We are the industry leader in Cards Issuance and Payments space - owing to our domain depth, variety of clientele, scale & size, value and impact to clients through Digital transformation and balanced global delivery footprint. Our aggregate ACV across these Card issuer and Payment companies relationships exceeds $100 million. Cards & Payments is the single largest practice within our Financial services portfolio. Some of our clients include leading Global Cards and Payment issuers, specialized prime and sub-prime card issuers, leading global Card network provider, Global fleet pre-paid cards provider, leading Remittance companies, mid sized and super regional banks, and more. Our industry expertise and leadership in this space has been recognized by analysts: Everest Group named Sutherland a Leader in its Payments Business Process Services (BPS) PEAK Matrix® Assessment 2025 (this ranking is across Cards and Payments), evaluated on both market impact and vision and capability. Our ranking on this Everest report are in fact higher than FIS itself. We have consistently grown, added new clients and expanded our offerings for Cards and Payment companies. Over the last 3 years, we have added 5 new clients in this space, launched two relevant offerings (Sutherland FRAML, Sutherland FinTelligent), which are geared to bring value and transformation to our clients. Our performance track record across issuer engagements reflects measurable, sustained outcomes: • TCO reduction of >30% through process digital transformation, re-engineering, right-shoring, and hyper-automation leveraging Sutherland's proprietary IP (Robility, FinXelerate, Fintelligent, CX360, Agent Assist, HelpTree, and Sentinel) • Customer journey ideation and redesign at Sutherland LABS, helping create new ways to interact and interface with end clients. • 98% KPI achievement consistently across active contracts • CXi (Customer Experience Index) improvement of >10% driven by our Design Thinking-based approach to process enhancement and omnichannel service delivery • Significant NPS uplift and measurable reduction in customer complaints, underpinned by real-time analytics and agent-assist tooling • Proven outcome-based and gainsharing commercial models, with co-investment commitments that align Sutherland's incentives directly with client value creation Sutherland's Cards and Payments services spans the full issuing value chain from onboarding and underwriting through account servicing, transaction processing, disputes and chargebacks, and FCC operations; supported by a balanced offshore and nearshore footprint that enables flexibility, seasonal scalability, and regulatory proximity.
4th Party / Sub-Contractor Management | Describe your approach to managing sub-contractors used in delivering TMS services. Confirm: (1) whether sub-contractors would be used on this engagement, which subcontractors would be used and where work would be performed; (2) your SLA flow-down mechanism; (3) whether the client retains audit rights over sub-contractors. | Our approach to managing sub contractors for TMS services is governed by a standardized third party risk management framework covering due diligence, contracting, information security, regulatory compliance, and ongoing performance oversight. Our foundational principle is straightforward; Sutherland remains the prime contractor at all times, and full accountability for delivery performance, service quality, and contractual obligations rests with Sutherland and not with any sub-contractor. 1. Use of sub contractors For this engagement, we may plan to use multiple sub-contractors. For e.g., we plan to use Uniphore as a specialized sub contractor to provide the unified desktop and real time agent assist solution that underpins our digital transformation and CX optimization objectives. Uniphore’s platform will be used to deliver unified agent workflows and real time guidance from approved locations, while all core service delivery, governance, and client facing roles remain with Sutherland as the prime contractor. We are utilizing Uniphore as a sub-contractor to provide AI services to FIS already. There maybe a need to evaluate possible use of additional sub-contractors to deliver services in EMEA region. We also constantly evaluate best in industry AI solutions to bring the best of global AI tools and technology to deliver the transformation solutions we are proposing as part of our response. Should any additional sub contractors be required as the engagement evolves, Sutherland will notify the client in advance, provide full details of scope, location, and controls, and obtain the client’s prior written approval before onboarding. 2. SLA flow down mechanism All SLAs, security, confidentiality, data protection, and regulatory obligations agreed with the client are contractually flowed down to our sub-contractors through back to back agreements that mirror the requirements in the prime contract. We operate a single integrated SLA and governance framework in which our sub-contractors performance is monitored alongside Sutherland’s operations via common dashboards and review forums, with defined remediation actions and the right to invoke service credits or adjust or terminate the sub contract arrangement in the event of persistent under performance. In summary, overall performance of this engagement (including anything sent to sub-contractor) will be the responsibility of Sutherland. 3. Client audit rights over sub contractors The client will retain full audit and inspection rights, as defined in the master services agreement, over material sub contractors used in delivering TMS services, including our sub-contractors. These rights (such as access to relevant records, processes, and control evidence, subject to reasonable notice and confidentiality) are embedded in our contract with our partner sub-contractors to ensure that the client’s and regulators’ audit and oversight requirements can be met seamlessly across the delivery chain.
Years of Experience — Risk Mitigation | How many years has your organization delivered end-to-end risk mitigation covering fraud, collections, disputes, and credit bureau management. Report the number of years your organization has continuously operated this function. Do not sum individual staff years across people — report the longest unbroken period your organization has actively delivered this service. | Sutherland has continuously delivered end-to-end risk mitigation services spanning fraud management, collections, disputes and chargebacks, and credit bureau management for over 15 years, with this fully integrated capability operational since 2010. This represents the longest unbroken period during which our organization has actively delivered all four functions as a cohesive service offering. Our Risk Management practice (FinCrime) is over 2500 FTEs across 28+ clients in Card issuers, Payment providers, Banks, Fintechs, Lenders, global e-com giants, retailers, Travel and Airlines and more. We have been rated as Star Performer -Financial Crime and Compliance (FCC) Operations Services PEAK Matrix® Assessment 2025. This rating validates our growing industry dominance and leadership in the FinCrime space. We provide end to end of FinCrime and Risk Management services which include Identity checks, KYC and Onboarding, Screening & Watchlists review, EDD investigations, Transaction Monitoring services, Alert remediations, Disputes & Chargebacks, Forensic audits, LOD 2,3 services, Risk Control and Testing. In Dec 2025, we announced a partnership with a leading Global AML platform provider (Comply Advantage). We provide "Compliance as a service" as part of this managed services offering that cuts across the entire FinCrime value chain. Over the last few years, we have developed numerous in-house AI solutions to help accelerate value for our clients. Some of these solutions include Disputes hyper-automation, KYC Onboarding tool, ID Scan and Fraud verification tool, PII data masking and compliance tool.
Years of Experience — Customer Care | How many years has your organization delivered customer care for card programs (commercial, consumer credit, debit, retail, loyalty, healthcare, prepaid). Scope includes: IVR and live agent handling, multilingual and after-hours support, lost/stolen servicing, and loyalty programs. Report the number of years your organization has continuously operated this function. Do not sum individual staff years across people — report the longest unbroken period your organization has actively delivered this service. | Sutherland has continuously delivered end-to-end customer care for 37 years now, and for card programs for over 18 years, with unbroken operations since 2007. This encompasses the full scope of card servicing including IVR and live agent handling, multilingual and after-hours support, lost/stolen card servicing, and loyalty program management. Our Customer services practice services over 50 clients today with 8,000 FTEs across various services and product lines. Our services span from Customer Insight and journey mapping to Onboarding and servicing operations, query resolutions across multiple channels (Voice, chat, email, social media), Retention, loyalty management. We provide Customer support across the Financial services portfolio, including multiple scenarios like Lost/stolen, Dispute resolution, Payment processing, loyalty management etc. As part of our Customer services portfolio, we provide "Customer services of the Future", which brings together the best of CX technology and Agentic AI solutions. We offer Omni-channel support through our own platform "Connect"; Agent productivity enhancement AI tools (e.g. Agent assit, GenAI based Knowledgebase, Unified Desktop); Agentic Conversational AI to enhance end customer experience, and reporting and management tools. We have delivered tremendous value to our clients in Customer services over the years including: - 40% TCO reduction - 15% CSAT Improvement - 10% improvement in First call resolution - 15% reduction in customer complaints Sutherland is an industry leader in providing Customer service, especially to Financial institutions. Our experience, depth of domain, AI led Digital transformation solutions puts us in the best position to continuously bring value to our clients.
Years of Experience — Back Office | How many years has your organization delivered back-office processing for card programs. Scope includes: imaging, correspondence processing, payment research, balance transfers, credit balance refunds, account maintenance, general ledger (GL) balancing and settlement, reconciliation of GL accounts, and returned mail processing. Note: application processing is not in scope for this engagement. Report the number of years your organization has continuously operated this function. Do not sum individual staff years across people — report the longest unbroken period your organization has actively delivered this service. | Sutherland has continuously delivered back-office processing for card programs for over 15 years now. We deliver or have delivered all back office scope items as detailed in this RFP. Our back office services include: Onboarding / application processing, pre-screening checks, compliance and KYC validations, Screening and Monitoring, activations and funding, account servicing and maintenance, waivers, card adjustments, claims adjudication, account closures, payments and remmitance exceptions processing, chargebacks and RegE disputes processing, Fraud prevention and investigations, reconciliations and GL balancing and settlements. We have over 2500 FTEs that deliver above back office functions across Cards, Payments, Retail banks, Lenders, Fintechs and BNPL providers. We also have a mailrooom facility in Tulsa, US with limited capacity to handle checks, return mails, imaging, lockbox etc.
Years of Experience — Client Operations Oversight | How many years has your organization delivered structured client-facing operational support. Scope includes: day-to-day client inquiry and escalation management, monthly and quarterly business reviews, and SLA monitoring. Report the number of years your organization has continuously operated this function. Do not sum individual staff years across people — report the longest unbroken period your organization has actively delivered this service. | Sutherland has delivered structured client-facing operational support, including day-to-day client inquiry and escalation management, monthly and quarterly business reviews, and SLA monitoring, for a continuous period of Thiry Five (35)+ years. Client facing operational support is embedded and delivered as part of every single operational services that we provide to our clients. We have done this for over 35 years, right from the time the company has started. Over years, we have developed structures, acquired and implemented best in class industry certifications (like ISO, PCIDSS) and introduced numerous AI platforms and tools to deliver these functions effectively for our clients.
Number of Active Financial Services Clients | How many active financial services clients does your organization currently serve? Break out by client type (issuer, acquirer, payments processor, other) where possible. | Sutherland currently partners with over 85 active banking and financial services clients worldwide, spanning card issuers, Retail and Commercial banks, payments and fintech providers, Lenders, Fintechs, BNPL providers, Asset managers and broader financial institutions globally. While we do not formally segment our active client count by issuer, acquirer, and processor in public disclosures, our portfolio includes clients across all three categories. Issuers and payments/fintech providers represent the majority of our active base, reflecting Sutherland's long-standing strategic focus on the card and payments ecosystem. Within the issuer segment specifically, Sutherland currently serves 3 of the top 5 card issuers globally, with coverage spanning consumer credit, debit, commercial, prepaid, and loyalty card programs.
Countries of Operation | In which countries do you currently deliver contact center or back-office services? Please list all the countries and sites you currently support. For each, indicate whether the site is company-owned or sub-contracted. | We deliver Customer services and / or back offices services from most of our site globally today. A list of some sites where we deliver these include: United States: Tulsa (OK), Rochester (NY), California, New Jersey, New York, Oklahoma, Virginia, and Work From Home across 45+ states in the US Canada: Windsor India: Bangalore, Bhopal, Chennai, Kochi, Mumbai, Hyderabad Philippines: CamSur, Carmona, Clark, Davao, Legazpi, Manila, Laoag, Palayan, Tarlac Bulgaria: Sofia, Varna, Burgas Colombia: Bogota, Barranquilla Egypt: Alexandria, Cairo Jamaica: Kingston Japan: Tokyo Kosovo: Pristina Malaysia: Kuala Lumpur Saudi Arabia: Riyadh South Africa: Pretoria and Johannesburg United Arab Emirates: Dubai United Kingdom: London China: Suzhou (Work From Home only) Portugal: Work From Home Sutherland operates over 60 operation centers and business operations in these countries. The majority of these sites are company-owned. Additionally, Sutherland has a robust Work From Home (WFH) model in several countries, including the United States, China, and Portugal. There is no indication in the context of sub-contracted sites; all referenced sites are either company-owned or operated directly by Sutherland.
Languages Supported | Which languages do you currently support across your delivery network? List associated delivery locations. Of particular relevance: English (US, CA, UK), Spanish (US), French-Canadian, German, Dutch, Portuguese. | Sutherland currently supports over 40 languages across its global delivery network, with associated delivery locations as follows: English: Supported in the United States (Tulsa, OK; Rochester, NY; WFH across 45+ states), Canada (Windsor), United Kingdom, Bulgaria (Sofia, Varna, Burgas), Kosovo (Pristina), Egypt (Alexandria, Cairo), China (Suzhou), Malaysia (Kuala Lumpur), Japan (Tokyo), Colombia (Bogota, Barranquilla), India (multiple cities), Philippines (multiple cities), Dubai (UAE), and other global centers. Spanish: Supported in the United States, Colombia (Bogota, Barranquilla), Bulgaria, and Mexico. French-Canadian: Supported in Canada (Windsor). German: Supported in Bulgaria (Sofia, Varna, Burgas), Kosovo (Pristina), Egypt (Alexandria, Cairo), India (select locations), Dubai (UAE). Dutch: Supported in Bulgaria (Sofia, Varna, Burgas). Portuguese (including Brazilian Portuguese): Supported in Colombia (Bogota, Barranquilla), Bulgaria, and Brazil. Additional languages supported include Arabic, Bahasa, Bulgarian, Burmese, Cantonese, Danish, Estonian, Finnish, Italian, Japanese, Korean, Malay, Mandarin, Norwegian, Polish, Russian, Swedish, Tagalog, Thai, Turkish, Vietnamese, and more. Sutherland leverages its sites in Eastern Europe, Asia Pacific, and Latin America as primary delivery locations for multiple languages in single locations, and bilingual support is available at several centers.
Overall Workforce | What is your total headcount across all geographies? Break out by: (1) front-office agent FTE; (2) back-office agent FTE; (3) support FTE (QA, WFM, Training, Management, Analytics); (4) approximate onshore / nearshore / offshore split (%). | Sutherland has a total headcount of over 55,000 full-time employees, with an additional 4,000–8,000 FTEs added during peak seasons. The breakdown by role function is as follows: Front-office agent FTE: 51% spread across 25% Customer Service (Customer Care), 13% Technical Support Helpdesk Digital Engineering Services, 7% Collections, 6% Sales, Customer Acquisition, Retention Back-office agent FTE: 31% spread across 16% Backoffice – Transaction Processing, 8% Finance & Accounting Services, 4% Content Moderation Management, 3% Research & Consulting Support FTE (QA, WFM, Training, Management, Analytics): 5% Support (HR, Infosec, QA, WFM, etc.), 6% Operations Management, 5% HR Services, 2% Admin Exec, 2% Quality, 1% WFM, 0.7% HR Training, 3.0% Service Delivery Management & Support, 0.3% Analytics The approximate onshore, nearshore, offshore split is: Onshore: 13% (North America) Nearshore: 17% (LATAM and Caribbean) Offshore: 70% (EMEA and APAC)
Agent Attrition — Last 3 Calendar Years | What were your voluntary agent attrition rates for each of the last three calendar years? Break out by geography where materially different. | Sutherland's attrition rate globally is between 3-3.65% for the last three years. Our attrition rates are some of the best in the industry, specially in US, LATAM and India which typically tend to experience higher attrition rates in the industry. Sutherland's global average voluntary attrition rate for front-line employees hired greater than 180 days is 3.65% per month, which equates to 44% annually for calendar year 2025. Attrition rates by geography for CY 2025 are as follows: Bulgaria 2.4%, Canada 3.8%, Colombia 4.6%, Egypt 4.9%, India 2.7%, Jamaica 4.4%, Kosovo 2.5%, Malaysia 2.4%, Mexico 2.6%, Philippines 3.9%, South Africa 3.2%, UAE 1.0%, and US 4.2%. Attrition for management and professional roles is significantly lower at 0.5% per month (6% annual).
Average Agent Tenure | What is your average agent tenure overall? Break out by primary function where available: Customer Service, Fraud Operations, Disputes & Chargebacks, Debt & Collections, Back Office, and Risk & Compliance. | Our current global average frontline agent tenure across financial services operations is approximately 2.3 years. By primary function, average tenure is: Customer Service 1.8 years; Fraud Operations 2.4 years; Disputes & Chargebacks 2.8 years; Debt & Collections 2.3 years; Back Office 3.5 years; and Risk & Compliance 3.8 years. These figures reflect actual time in role and are not based on summed staff experience
Agent Qualifications | Optional. Are there any industry-relevant certifications, training frameworks, or accreditations held by your workforce that are applicable to financial services contact center operations? | Sutherland’s workforce holds a comprehensive suite of industry-relevant certifications, training frameworks, and accreditations applicable to financial services contact center operations. These include PCI, ISO 27001, ISO 27701, ISO 9001, ISO 14001, ISO 45001, P-CMM Level 5, Six Sigma, HIPAA, GDPR, EU-U.S. Privacy Shield Framework, and COPC. In additional, For Financial services industry, based on role and job requirement, we have resources certified as CFE, ACAMS, Internal Audits, ABA, NMLS, FCA amongst others. We either hire resources with these certifications or sponsor and certify our resources on these based on job requirements. Sutherland also participates in the EcoVadis sustainability assessment and utilizes Trustwave’s TrustKeeper Compliance Validation Service for PCI DSS. The organization maintains a large in-house talent pool trained in COPC standards and Six Sigma methodologies, and operates under a Service Excellence Framework based on best practices. Additionally, Sutherland provides targeted ethics and compliance training, including anti-fraud, anti-money laundering, and anti-bribery policies, and supports ongoing regulatory financial compliance training for all employees. For financial services programs, Sutherland employs licensed mortgage loan officers and insurance representatives, ensuring all required state and federal licenses are obtained and maintained through structured training and continuing education. The organization also leverages resources such as Thomas Reuters for International Banking Regulations and BAI Learning Management for U.S. Banking and Financial Regulations as needed. Sutherland maintains role-based training and governance frameworks relevant to financial services contact center operations, including information security, data protection, process excellence, and simulation based operational training. Where applicable, our teams also operate within regulated control environments aligned to card-payment and financial-services requirements

## 3.0 Relevant Experience
3.0 Relevant Experience
Provide three case studies and three client references on comparable engagements. Case studies should reflect large-scale, regulated financial services BPO. At least one must involve a migration of 300+ FTE.
3.1 Case Studies
Select engagements that reflect large-scale, regulated financial services BPO. At least one must involve a migration of 300+ FTE. Include one engagement where challenges were encountered — describe what happened and how they were resolved.
# | Industry & Client Type | Scale (FTE / Volume) | Services Provided | Geographies & Languages | Transformation Levers Applied | Measurable Outcomes | Challenges & Resolution
1 | FIS | 550+ | End to End Back Office and Front Office for CIM and Banking | Delivery Geos - US & India Languages: English | Hyper-automation, Conversation AI, Agent Assist, Unified desktop, GenAI Knowledge mgmt. | 55% Committed productivity 40% cost reduction underwritten by Sutherland 90%+ re-badge | Challenges / Objectives: Client faced high operational costs, poor customer/agent experience, limited digital adoption despite tech investments, and fragmented operations across GCC and multiple vendors. The Sutherland Transformation: Client selected Sutherland to provide L1/L2 CX and back-office support across Payments, Cards, Retail banking, Fraud alerts and Disputes. Sutherland executed a 5-year TCO-led transformation model with e2e process and digital transformation. Model had benefits front-loaded with risk-mitigated transformation roadmap to increase Y-On-Y savings We designed a tailored transformation roadmap leveraging levers such as Lean Six Sigma led process optimization, hyper-automation, Conversational AI, Agent Assist, Unified Desktop, and GenAI knowledge management. We committed to a custom commercial and target operating model with 40% cost reduction underwritten by Sutherland, 90%+ re-badge for ops consolidation/continuity, and 55% productivity gains.
2 | FISERV | 2000+ | Card Services, Clover Support, Payment Services, Credit Union Solutions, Biller Services, Disputes & Fraud, Data security , Merchant POS support, Technical support and compliance | Delivery Geos: India, LATAM, EMEA Languages: English, Spanish, German & Polish | Transformation Led operations backed by Design Labs, Sutherland Digital tools and partnerships | 30% TCO reduction through innovative commercial models, digital transformation 100% Compliance on PII data masking 100% NPS rating over last 7 years | Challenges / Objectives: A leading global fintech provider faced spiraling costs, fragmented siloed processes, high fraud losses, poor customer satisfaction, and data security risks from thousands of client systems, needing rapid tech stack optimization and intelligent automation The Sutherland Transformation: Full process redesign and optimization while integrating clients siloed systems for best risk mitigation and compliance. A right-shoring strategy, enabling a phased transition to Sutherland's Banking and Financial Services Centers of Excellence around the globe. Sutherland Sentinel AI deployed to give real-time employee authentication with data masking of PII data for all client systems. Sutherland Connect, Speech Analytics, and intelligent automation via Sutherland Robility and Sutherland Extract, transforming their operating model.
3 | BLOCK | 2000+ | Scams, Frauds & Disputes, Accounts Settings, Priority Banking, Customer Care, Cash Cards, Tech support, Borrower support & Money Movements | Delivery Locations: India & Philippines Language: English | Developed a digital and process re-engineering solution tailored to client’s operating model tied to outcomes | Committed 25% TCO reduction via ops excellence, digital and operating model interventions Guaranteed 20% ramp with a 30-day notice period Committed 15-20% internal seeding for new LOB launches | Challenges / Objectives: Client needed a strategic global partner for growth/consolidation, domain expertise across front-middle-back office functions with AI/tech, rapid scaling, and outcome-based commercials to hit Rule of 40 while cutting costs and boosting quality/service. Client expected high scalability and agility to rapidly adopt to their dynamic business needs. The Sutherland Transformation: Nimble global right-shoring model implemented across 2 sites in Philippines and India in a brick & mortar operating model Designed CoE led delivery model. CoEs set up for CX, Back Office and Risk Operations delivery across 2 countries with embedded domain SMEs Deployed 25-30 Fraud and Risk domain experts & trainers for seamless lauch and BAU Seeded the program with 15% internal SMEs and consultants for an accelerated ramp Developed a digital and process re-engineering solution tailored to client’s operating model tied to outcomes Built an outcome based commercial model with committed gains and timelines
3.2 Client References
References must be contactable and from current or former financial services clients on comparable engagements. At least one reference should be able to speak to a transformation or large-scale migration program.
# | Company Name | Reference Name & Title | Contact Information | Nature of Engagement | Additional Notes
1 | To be provided later on request
2 | To be provided later on request
3 | To be provided later on request

## 4.0 Workforce & Delivery
4.0 Workforce & Service Delivery
This tab covers eigh areas: (1) language capabilities, (2) rebadging scope (3) rebadging / offshoring schedule (5) staffing model, (6) cost impacts, (7) SLA Adherance, and (8) Change Management Approach. Responses across sections should be consistent with each other and with your pricing in sheet 6.0.
4.1 Language Capabilities
Confirm your ability to support each language. For each language, list the delivery location(s) you would use to support it.
Language | Can You Support? (Y/N) | Primary Delivery Location | Secondary Location | Tertiary Location | Volume / Threshold Notes
English (US) | Y | Philippines | India | South Africa
English (UK) | Y | Philippines | India | South Africa
English (Canada) | Y | Philippines | India | South Africa
Spanish (US) | Y | Dominican Republic | Colombia
French-Canadian | Y | Canada | Egypt |  | Limited capacity in secondary locations
German | Y | Bulgaria | South Africa |  | Limited capacity in secondary locations
Dutch | Y | Bulgaria | South Africa |  | Limited capacity in secondary locations
Portuguese | Y | Bulgaria | Colombia |  | Limited capacity in secondary locations
4.2 Site Rebadge Approach
TMS currently operates across seven sites across North America (North America) and Europe, Middle East & Africa (EMEA). For each site, indicate your intended approach. Headcount figures will be provided in the data appendix.
Site | Region | Intend to Take Over Site? (Y/N) | Target Transition Date | Approach (Workforce Only / Site + Workforce / Neither) | Approx. FTE at Site (post-transition) | Considerations & Assumptions
US — Columbus, GA | North America | N | 17 Aug 2026 to 28 Aug 2026 | Site sub-lease + Workforce | 1073 | 5% attrition after rebadge announcement is made. Rebadging to be done across mutliple dates and in batches within 2 weeks.
Canada — Sudbury | North America | N | 31 Aug 2026 to 4 Sep 2026 | Site sub-lease + Workforce | 64 | 5% attrition after rebadge announcement is made.
Philippines — Manila | North America / Offshore | N | 17 Aug 2026 to 21 Aug 2026 | Site sub-lease + Workforce | 87 | 5% attrition after rebadge announcement is made.
UK — Milton Keynes | EMEA | N | 31 Aug 2026 to 4 Sep 2026 | Site sub-lease + Workforce | 702 | 5% attrition after rebadge announcement is made.
UK — Coventry | EMEA | N
Netherlands — Barneveld | EMEA | N | 7 Sep 2026 to 11 Sep 2026 | Site sub-lease + Workforce | 126 | 5% attrition after rebadge announcement is made.
Germany — Hamburg | EMEA | N | 7 Sep 2026 to 11 Sep 2026 | Site sub-lease + Workforce | 213 | 5% attrition after rebadge announcement is made.
4.3 Employee Transition Terms
State your position on each commitment. Note conditions or constraints where you cannot fully commit.
Rebadging Ease of Transition | Response
Same salaries offered to rebadged employees? (Y/N) | Y
Same benefits offered to rebadged employees? (Y/N) | Y
Retention bonus to be paid? (Y/N) | Y* | * Retention bonus to be paid for select key employees only
Severance to be paid if employees are downsized? (Y/N) | N* | * Current commercial proposal does not assume Severance cost to be paid by service provider as we do not have any employee level data available
4.4 Legacy IT & Site Asset Acquisition
For each asset, confirm acquisition intent and proposed transfer date. Where declining, state your transition assumptions.
Legacy IT and Site Infrastructure | Will the technology be acquired? (Y/N) | Transfer Date
Technology Licenses | Yes | As per migration schedule provided
Laptops | Yes | As per migration schedule provided
Site specific networking components | Yes | As per migration schedule provided
Other
4.5 Role-Level Rebadge & Retention Scope
For each function and site, confirm whether staff are in scope for rebadging and retention bonus eligibility.
Will these resources be rebadged? (Y/N)
Functions Specification | US — Columbus, GA | Canada — Sudbury | Philippines — Manila | UK — Milton Keynes | UK — Coventry | Netherlands — Barneveld | Germany — Hamburg | In-scope for retention bonus? Y/N
WFM | Y | Y | Y | Y | Y* | Y | Y | Y
Training | Y | Y | Y | Y | Y* | Y | Y | Y
Quality | Y | Y | Y | Y | Y* | Y | Y | Y
Customer Service | Y | Y | Y | Y | Y* | Y | Y | Y
Loyalty | Y | Y | Y | Y | Y* | Y | Y | Y
Disputes Inbound | Y | Y | Y | Y | Y* | Y | Y | Y
Fraud Inbound | Y | Y | Y | Y | Y* | Y | Y | Y
Fraud Outbound | Y | Y | Y | Y | Y* | Y | Y | Y
Fraud Strategy | Y | Y | Y | Y | Y* | Y | Y | Y
Back Office Disputes | Y | Y | Y | Y | Y* | Y | Y | Y
Off Phone | Y | Y | Y | Y | Y* | Y | Y | Y
Accounting | Y | Y | Y | Y | Y* | Y | Y | Y
Reporting | Y | Y | Y | Y | Y* | Y | Y | Y
Collections | Y | Y | Y | Y | Y* | Y | Y | Y
IVR/Tech | Y | Y | Y | Y | Y* | Y | Y | Y
Senior Leadership | Y | Y | Y | Y | Y* | Y | Y | Y
* No FTE numbers provided in Appendix A and D against Coventry site.
4.6 Location Model
For each service tower, describe how you propose to rebadge or offshore and nearshore delivery over the contract term in a location migration plan. Vendor to add additional sites locations the work will be transitioned to as necessary. Vendors should propose the delivery footprint they believe is optimal to achieve the efficiency outcomes described in the RFP, within the client and regulatory constraints identified. Clearly state your assumptions and the sequencing rationale. Note: your full list of current operating locations should be declared in tab 2.0 under Countries of Operation and not necessarily repeated here.
Current Host Location | Future Host Location | End State, How many FTE will Remain at this location? (Provide as a % of the current site FTE counts)
US — Columbus, GA | Philippines & India | 5% | 5% FTEs retained in US. We propose to retain 5% staff onsite. This may change as the solution evolves.
Canada — Sudbury | Philippines & India | 49% | 49% FTEs retained in Canada
Philippines — Manila | Clark, Philippines | 100% | 100% of the initail FTEs retained in Philippines; additionally Englsih voice FTEs from North America and EMEA migrate to Philippines
UK — Milton Keynes | Philippines & India | 0% | 0% FTEs retained in UK.
UK — Coventry | Philippines & India | 0% | 0% FTEs retained in UK.
Netherlands — Barneveld | Bulgaria, Philippines & India | 0% | 0% FTEs retained in Netherlands.
Germany — Hamburg | Bulgaria, Philippines & India | 0% | 0% FTEs retained in Germany.
Add additional locations as desired |  | TBD | TBD
4.7 SLA & KPI Improvement Commitments
Demonstrate the expected improvement in SLAs/KPIs over time, from transition through steady state. Proposed commitments may be incorporated into contractual service level schedules.
SLA/KPI | Current Levels | Future Levels | Improvement Approach | Time to improvement
| SLA/KPI | SLA/KPI | Vendor to provide approach to improving SLA / KPI | Vendor to provide improvement timing
CSAT | 78-80% | 86-90% | Complete VOC deep-dive within first 30 days to identify top 5 drivers Implement CX-focused QA scorecard (100% alignment within 2 weeks) Drive bottom quartile agent improvement plan (weekly tracking) Launch real-time supervisor call interventions for critical interactions Establish closed-loop feedback mechanism with FIS for policy/process fixes | Stabilization by 60–90 days Full uplift by 120–150 days Measure of Success : +3% CSAT uplift within 45 days Bottom quartile reduced by 50% within 60 days QA–CSAT correlation improved to >85% alignment Sustained CSAT ≥ 86% by Day 90+
AHT | Indexed at 100 (baseline) | 88–92 (8–10% reduction) | Complete call driver analysis within 30 days (top 80% volume drivers) Deploy macros / agent assist tools for top call types Enforce hold time and ACW thresholds via real-time dashboards Redesign knowledge base for top 20 call drivers Run weekly lean sprints targeting repeat contacts and handoffs | Stabilization within 30–45 days Full improvement by 90–120 days Measure of success : Return to baseline within 30–45 days 80% adoption of tools/macros within 60 days ACW reduced by 15–20% within 75 days Sustained AHT reduction of 10–15% by Day 90+
ASA | ~45–60 seconds | 30–40 seconds (10–15% improvement) | Improve forecast accuracy to >95% within 45 days Implement real-time adherence tracking with hourly interventions Enable cross-skilled agent pools for peak intervals Deploy intra-day re-forecasting and queue rebalancing Tighten shrinkage controls and schedule compliance rigour | Stabilization within 30 days Full improvement by 60–90 days Measure of success : Adherence ≥ 92% within 30 days Shrinkage variance reduced to <3% within 60 days 90% intervals meeting staffing requirement by Day 60 Sustained ASA ≤ 35 seconds by Day 75–90
FCR | 68-72% | +10–15% improvement within 90 days | Identify top repeat call drivers (within 30 days) and eliminate root causes Implement resolution checklists for top 20 call types Strengthen agent decisioning capability through scenario-based training Enable real-time SME/coach support for complex queries Align KB content to resolution-first approach (not process-first) | +5% FCR uplift within 45 days Repeat contacts reduced by 20% within 60 days 90% adherence to resolution checklists Sustained FCR ≥ 80% by Day 90+
Error Rates | 8-10% | 50–60% reduction within 90 days | Define and enforce critical vs. non-critical error framework Launch daily QA audits for bottom quartile agents Implement error-proofing mechanisms (checklists, system validations) Conduct weekly error trend analysis and targeted refreshers Introduce pre-dispatch quality checks for high-risk transactions | 30% reduction in defects within 45 days Critical errors near-zero (<1%) within 60 days Bottom quartile error rate improved by 50% Sustained defect rate ≤ 4% by Day 90+
Compliance | 90-92% | Achieve and sustain 98–100% within 60–90 days | Deploy mandatory compliance certification (100% completion) within 30 days Introduce real-time compliance alerts and call monitoring Enforce zero-tolerance policy for critical compliance breaches Conduct daily compliance huddles for high-risk queues Align QA scorecards with higher weightage on compliance metrics | 100% agent certification within 30 days Critical compliance breaches reduced to zero within 45 days QA compliance adherence ≥ 98% by Day 60 Sustained compliance at 99%+ by Day 90+
Backlog/Ageing | Indexed at 100 (baseline) | 70–80% reduction within 60 days; steady-state control thereafter | Complete backlog segmentation (age, complexity, priority) within 2 weeks Launch dedicated backlog reduction sprint teams Introduce aging-based prioritization (TAT-driven closures) Increase throughput via extended hours / surge capacity (short-term) Eliminate upstream drivers creating new backlog | 40% backlog reduction within 30 days 70% reduction within 60 days Zero critical aging backlog (>X days) by Day 60 Steady-state backlog maintained within BAU thresholds by Day 90+

## 5.0 Technology Solution
5.0 Technology Solution
This tab covers four areas: (1) technology capability mapping — current TSYS applications and expected future-state are pre-populated for reference; respond with your proposed solution and migration approach; (2) technology governance commitments; (3) AI overlay capabilities; (4) Technology Costs You Are Willing to Fund and (5) a Technology responsibility Matrix between yourself and FIS/TSYS; The migration approach and target architecture columns are intentionally open. FIS is not prescribing a migration methodology or architecture pattern. Vendors should propose the approach they would actually use based on the current and future-state stack shown. Responses that reflect a genuine assessment of the TSYS-to-FIS technology context will be evaluated more favorably than generic migration frameworks.
5.1 Technology Capability Mapping & Migration Plan
Columns D and E show the current TSYS application and the expected future-state application for reference. Where no future-state equivalent exists, the TSYS application will be retained. Provide your proposed solution, migration approach, and costs.
Capability | Technology Type | Current TSYS Application | Future-State Application (if no equivalent, TSYS retained) | Phasing Strategy | Proposed Sequencing | Migration Approach | Target Architecture Pattern | Data Migration Approach | Estimated Start Date | Cutover Duration | Key Dependencies | Key Risks
Communications Management | Voice (Inbound/Outbound) | Avaya (CM, AAEP, AES, CBA, Session Mgr, SBCE) | NICE CXone | Controlled phased migration (Outbound → Inbound) with coexistence | 1. NICE CX one setup 2. Outbound migration (pilot → scale) 3. Inbound routing & number strategy 4. Queue-wise migration (CS → Fraud → Disputes → Collections) 5. Stabilization & decommission | Parallel-run with SIP trunking; outbound first; inbound via porting/forwarding; rollback supported | Cloud CCaaS (NICE CXone) with SIP (Lumen) | Config-driven; no bulk migration; legacy recordings retained | Phase 1 | Outbound: 2–3 weeksInbound: 3–5 weeks per queue | NICE readiness, telecom (Lumen), network QoS, training | Number portability delays, compliance validation, coexistence complexity
| Chat / Secure Messaging | AWS Connect (in deployment) | AWS Connect | Stabilize and enhance current deployment; no re-platforming | 1. Complete rollout 2. Standardize routing & SLAs 3. Align workflows 4. Integrate with reporting 5. Enable optional NICE orchestration | Enhancement-led; API-based integration; no migration | Distributed omnichannel (AWS Connect for chat, NICE CXone for voice) | No migration; data remains in AWS; API exposure for analytics | Immediate | No formal cutover; 2–4 weeks stabilization | AWS Connect readiness, reporting integration | Channel fragmentation, cross-channel agent limitation
IVR / CTI | Touchpad IVR | Avaya Aura Experience Portal | NICE CXone (IVR module) | Parallel IVR rebuild and phased migration aligned with voice | 1. Capture current IVR flows 2. Rebuild in NICE Cxone 3. Integrate authentication (CRM/API) 4. UAT & validation 5. Gradual cutover by queue | Rebuild + parallel validation; phased traffic migration | NICE CXone IVR as centralized IVR layer | Reuse prompts; no data migration | Phase 1 | 2–3 weeks per IVR flow | IVR design validation, API readiness | Flow mismatch, customer experience disruption
| Conversational / AI-based IVR | AWS Connect (in deployment) | AWS Connect | Continue deployment and enhance NLP capabilities | 1. Complete rollout 2. Train NLP models 3. Expand use cases 4. Integrate analytics | Enhancement-driven; no migration | AWS-based conversational AI IVR integrated with NICE CXone | No migration; training via historical data | Phase 2 | Iterative rollout | Availability of training data | NLP accuracy, training dependency
| Screen Pop with Call / Contact | Avaya CTI / Avaya Workspaces (EMEA) | NICE CXone (screen pop module) | CTI integration aligned with pilot migration | 1. Integrate NICE CXone with DSP/CRM 2. Validate screen pop3. UAT across use cases | API-based CTI integration | NICE CXone + Digital Servicing Platform (DSP) | No migration | Phase 1 | 2–3 weeks | CRM/API availability | CTI latency, data mismatch
Routing | Skills-Based Routing | Avaya CM / AES | NICE CXone | Recreate routing logic during migration | 1. Capture routing rules 2. Configure NICE routing 3. Validate in UAT | Configuration-driven migration | NICE CXone routing engine | No migration | Phase 1 | Included in voice cutover | Routing logic validation | Misrouting risk
| Advanced Routing (customer attribute-based) | Avaya CM / AES | NICE CXone | Enhance routing with customer attributes | 1. Analyze current logic 2. Implement attribute-based routing3. Optimize continuously | Rebuild with enhancements | NICE CXone AI-driven routing | No migration | Phase 2 | Iterative | Data availability from TSYS | Incorrect routing logic
CRM / Case Management | Customer Authentication | Avaya CTI / step-up auth tools | NICE CXone | Rebuild authentication integrated with backend systems | 1. Define auth flows2. Integrate APIs3. Validate in UAT | API-driven authentication | NICE CXone integrated with TSYS | No migration | Phase 1 | Included in IVR/CTI | Backend API readiness | Authentication failure risk
Agent Desktop | Agent Desktop Simplification / Consolidated Desktop | TS1 / TS2 Mainframe Green Screens; TCS (Pega) | Digital Servicing Platform | Enable DSP as unified desktop | 1. DSP readiness 2.Integrate apps 3. UAT validation | Integration-led (no replacement of backend) | DSP as unified UI over TSYS | No migration | Phase 2 | 3–5 weeks | DSP readiness | Adoption risk
QA — Recording & Scorecards | Call / Contact Recording | Avaya/Verint WFO; NICE Call Recording (North America); Avaya/Verint WFO (EMEA) | NICE CXone (recording module) | Gradual shift to NICE recording | 1. Enable NICE recording 2. Validate compliance 3. Phase out legacy | Parallel recording validation | NICE CXone recording | Historical retained | Phase 1 | 2–3 weeks | Compliance validation | Recording gaps
| Screen Capture | Avaya/Verint WFO; Desktop & Process Analytics (EMEA) | NICE CXone | Implement with voice sync | 1. Configure NICE screen capture 2. Validate | Configuration-driven | NICE CXone | No migration | Phase 2 | 2–3 weeks | Tool readiness | Sync issues
| Quality Scorecard & Review | Avaya/Verint WFO (Quality Monitoring, Form Designer) | NICE CXone | Transition to AI-based QA | 1. Recreate scorecards 2. Enable AI scoring | Transformation-led | NICE CXone QA analytics | Migration of templates | Phase 3 | Iterative | AI readiness | Model accuracy
Speech & Text Analytics | Compliance Monitoring | Avaya/Verint WFO (compliance recording) | NICE CXone | Enable AI analytics across channels | 1. Enable voice analytics 2. Integrate chat data 3. Expand coverage | AI overlay integration | NICE CXone analytics | No migration | Phase 3 | Iterative | Data ingestion readiness | Accuracy risk
Workforce Management | Strategic & Tactical Forecasting | Avaya/Verint WFO (Strategy Planner + WFM) | NICE CXone (WFM module) | Consolidate WFM across channels | 1. Enable NICE WFM 2. Integrate voice + chat 3. Validate forecasting | Lift-and-enhance | NICE CXone WFM unified | No migration | Phase 3 | 3–5 weeks | Data integration | Forecasting inaccuracies
5.2 Technology Governance Commitments
For each commitment below, state your position clearly. Where you cannot fully commit, describe the conditions or constraints that apply.
Requirement | Vendor Position (Commit / Partial / Cannot Commit) | Details, Conditions, or Constraints
Confirm you will provide open APIs with no data lock-in and full interoperability. | Partial Commit | Applicable for all FIS extended technology (Nice CX, AWS, DSP etc) . Unmapped Systems details to be clarified in Workshop 1
Confirm the FIS/TSYS retains full ownership of all data at all times, including during and after transition. | Commit | Applicable for all FIS /TSYS owned technology items
Confirm no proprietary data formats will be used — all data exportable in standard formats at any time. | Commit | As layed out by Nice CX, AWS and DSP
Confirm full data extraction rights upon contract exit, at no additional cost to the client. | Cannot Commit | On external Service providers viz. AWS, FIS extended technologies
Confirm you can provide a side-by-side coexistence environment for a minimum 12-month dual-run period. | Commit | SG will support a parallel run for a phased client cutover
Confirm you will fund technical debt remediation where your technology introduction creates new technical debt. | Partial Commit | Based on Unmapped Systems details to be clarified in Workshop1
Confirm you will provide AI governance documentation covering bias monitoring, model drift, and explainability for all AI tools deployed. | Commit | Applicable for Sutherland provided AI services.
Confirm AI overlays can be integrated via API without requiring migration of core telephony or processing platforms. | Commit | SG AI services can integrate with existing FIS technology stack (Nice CX, AWS and DSP)
Confirm the client retains ownership of telephony infrastructure and IVR design unless explicitly agreed otherwise. | Commit | FIS owned Nice CX
Confirm a full coexistence architecture plan will be provided prior to go-live, covering the full transition period. | Commit | SG will Co-Develop and define all Architecture plans, Delivery timelines and share with FIS as part of the planning and execution phases.
Confirm all tooling (including AI Overlays) will be pre approved by the FIS/TSYS Governance team, comprised of architecture, AI Governance and Security Operation, prior to implementation. | Commit | Sutherland will submit all design & development documents to the Governace and Architecture Review Board (ARB) for approvals and update as needed based on feedback
Confirm you will provide quantified, contractually referenceable projections of AHT reduction, call deflection, and cost impact from AI overlays. | Partial Commit | Requires study of current process and propose new process to suit FIS technology. This is a joint effort with FIS,TSYS and Sutherland team
5.3 AI Overlay Technology
Describe the AI overlay tools you propose to deploy as part of this engagement. For each, describe the capability, quantify the anticipated operational impact, and confirm how it integrates with the existing technology stack. Summarize your total efficiency ambition across all three levers. All figures in USD millions, rounded to one decimal place (e.g. $2.4M). Clearly state which savings are contractually committed.
Tooling & AI Overlay Technologies | Category (e.g. NLP, GenAI, RPA, Predictive) | Description | Primary Value Lever (Digital Efficiencies, Labor Arbitrage, Productivity) | Quantified Impact (e.g. X% AHT reduction, Contact Elimination) | Timeline to Deploy | Integration Method (API / Native / Other) | Proposed Application to Integrate With | Key Assumptions / Dependencies | Total Opportunity ($M relative to Direct Costs) | Year 1 Benefit ($M) | Year 2 Benefit ($M) | Year 3 Benefit ($M) | Steady State (Y4) Benefit ($M) | Steady State (Y5) Benefit ($M) | Contractually Committed? (Y/N) | Can any technologies be decommissioned/rationalized as a result of this AI overlay? Please identify the impacted applications.
AI enabled Intelligent Virtual Agent (IVA) for voice contact containment | TTS, STT, NLP, Gen AI, LLM | Virtual voice agents for automated conversations with customers and resolution of requests by registering request or providing required information | Digital efficiency | 5 % of the inbound volume will be contained resulting in 75 FTE reduction for NA (from 1283 to 1208 FTE) and 99 FTE for EMEA (from 1096 to 997) | 17th month from go-live of the program. With development cycletime of 16 weeks | API | CRM, Nice CX One, IVR, Core Banking Applications based on automation use cases | 1) 6 months for the migration from TSYS to FIS stack of technology 2) Successful due diligence & feasibility study and requirement confirmation | To Be shared | To Be shared | To Be shared | To Be shared | To Be shared | To Be shared |  | No
AI enabled Unified Desktop with Knowledge Assist to augment voice agents | GenAI, NLP, Predictive Analytics | Unified agent workspace with real-time transcription, contextual knowledge retrieval (KB), next-best-action prompts, compliance guidance, and auto-summarization | Digital efficiency | AHT saving of 5% for overall volume handled by the human agents with resultant FTE reduction of 51 for NA and 34 for EMEA | 8-12 weeks | API + Desktop Embed (Chrome Extension / iFrame / Native SDK) | NICE CXOne (Telephony), Knowledge Base, Internal KBs, CRM | Requires access to knowledge sources, historical interaction data for model training, real-time voice stream availability, CRM integration, and defined compliance workflows | To Be shared | To Be shared | To Be shared | To Be shared | To Be shared | To Be shared |  | No
Agentic AI driven containment of back‑office processes | RPA, AI Agent, LLM | Automation of back office processes using a combination of RPA and AI Agents equipped with NLP, GenAI & LLM capabilities | Digital efficiency | 25% consultant effort reduction therefore saving 28 FTE in NA and 10 FTE in EMEA | 12th month from go-live of the program. With development cycletime of 6 to 16 weeks based on the complexity of the solution | API & UI | CRM & Core Banking Applications based on automation use cases | Successful due diligence & feasibility study and requirement confirmation | To Be shared | To Be shared | To Be shared | To Be shared | To Be shared | To Be shared |  | No
AI enabled Chatbot for voice contact deflection | NLP + GenAI | Deflect simple, high‑volume inquiries from inbound voice into Chatbot with seamless handoff (with full context) to live chat/voice when needed | Digital Efficiencies | ~20% of the voice contact can be handled through chat medium (chatbot + human agent) which helps in saving 93 FTE in NA and 21 in EMEA | 14th Month from go-live with development cycletime of 12 weeks | TBU | CRM, Knowledge Management, Nice CX One, CTI | 1) 6 months for the migration from TSYS to FIS stack of technology | To Be shared | To Be shared | To Be shared | To Be shared | To Be shared | To Be shared |  | No
Contact deflection through Messaging services | NLP + Messaging (SMS) | Automating customer requests on WhatsApp | Digital Efficiencies | Deflect 2 % of volume to Text, which will help in saving effort of 26 FTE in NA and 14 FTE in EMEA | 4 months | API (messaging gateway + CX platform) | NICE Digital (Messaging), SMS gateway (e.g., Twilio), CRM, Core Banking Applications based on automation use cases | Opt‑in/consent, opt‑out handling; no PAN over SMS (PCI); secure links for authentication; short‑code provisioning; coexistence with IVA/voice; client‑by‑client enablement. | To Be shared | To Be shared | To Be shared | To Be shared | To Be shared | To Be shared |  | No
5.4 Vendor Funded Technology Costs
Cost Types | Total to Be Funded by the Vendor ($M)
Phase 0 — Mobilization & Foundation | 0.70138
Phase 1 — Pilot | 0.71021
Phase 2 — Scale (Customer Service + Fraud) | 1.5085
Phase 3 — Scale + Global - EMEA Rollout | 2.083
Phase 4 — Hypercare | 0.26602
Total | 5.2691
5.5 Technology Responsibility Matrix
Populate a RACI of what TSYS/FIS will be responsible for and what you will be responsible for. Please augment the table as you see fit.
Activity | TSYS/FIS | Sutherland
Strategy & Planning
Business Requirements Definition | R, A | C, I
Technical Requirements Definition | A, C | R, I
Architecture Design | C, I | R, A
Migration Strategy | A, C | R, I
Implementation Roadmap | C, I | R, A
Environment Planning | A | R, C
Design
Application Configuration Design | A, C | R, I
Integration Design | A, C | R
Data Mapping Design | C, I | R, A
Security and Controls Design | A, C | R
Test Strategy Development | A, C | R, I
Build & Configuration
Platform configuration | C, I | R, A
Integration Development | C, I | R, A
API Setup | C, I | R, A
Workflow Configuration | A, C | R, I
Automation Setup | C, I | R, A
Reporting Configuration | A, C | R, I
Testing
Unit Testing | C, I | R, A
System Integration Testing (SIT) | A, C | R, I
Data Validation | A, C | R, I
User Acceptance Testing (UAT) | A, C | R, I
Performance Testing | A, C | R, I
Security Testing | A, C | R, I
Migration & Cutover
Data Migration Execution | C, I | R, A
Parallel Run | A, C | R, I
Cutover Planning | A, C | R, I
Production Deployment | A, C | R, I
Go-Live Support | A, C | R, I
Stabilization
Hypercare Support | C, I | R, A
Incident Management | R | A
Defect Remediation | C, I | R, A
Performance Monitoring | C, I | R, A
Ongoing Managed Services
Incident Management | A, C | R, I
Project Management | A, C | R, I
Dependendency Management | A, C | R, I
Change Management | A, C | R, I
Release Management | A, C | R, I
Enhancement Management | A, C | R, I
Continuous Improvement | A, C | R, I
Platform Support | A, C | R, I
5.6 Assumptions
Category | Assumption
Delivery Model | The program will follow a phased, capability-led migration approach with staggered overlapping waves (not big-bang). The Schedule will be agreed upon with FIS leadership
Timeline | Total program duration is 20 months, including 18 months migration + 2 months hypercare.
Execution Model | Delivery will transition from a centralized model (Phase 1–2) to a squad-based model (Phase 3–4) with 2–3 parallel squads.
Resource Model | A global delivery model will be used with ~80% offshore and ~20% onshore resources.
Peak Team Size | Peak team size is estimated at ~35–40 resources during Phase 3 (complex rollout).
Platform Strategy | NICE CXone will serve as the primary engagement platform for voice, IVR, routing, WFM, and analytics.
Digital Channels | AWS Connect will be retained for chat and conversational flows unless otherwise directed by FIS.
Legacy Systems | Avaya and Verint platforms will be maintained in coexistence mode during migration and decommissioned post-stabilization.
Mainframe Systems | TSYS (TS1/TS2) will remain the system of record and will be integrated via APIs; no core replacement is assumed.
Integration Approach | All integrations will be API-driven, leveraging middleware and secure service layers for TSYS and third-party systems.
Data Migration | No full data migration from TSYS is assumed; real-time data access via APIs will be used. Historical data will remain in source systems unless required.
Telephony | Telephony services (e.g., SIP, toll-free numbers via Lumen) will be available and portable for migration to NICE CXone.
Environments | FIS will provide required environments (Dev, QA, UAT, Prod) or approve cloud provisioning for the same.
Access & Security | Required access to TSYS systems, APIs, and third-party platforms will be provided with appropriate security approvals.
Compliance | All solutions will comply with PCI DSS, data privacy, and regional regulatory requirements (NA & EMEA).
Testing | Business users will support UAT cycles and sign-offs as per agreed timelines.
Training | FIS will support agent participation for training and transition activities.
Change Management | Organizational change management and communication support will be jointly managed with FIS stakeholders.
Dependencies | External dependencies (e.g., telecom providers, third-party fraud systems) will meet agreed timelines.
AI Enablement | AI capabilities (IVR, analytics, automation) will be implemented as overlay solutions without requiring core system replacement.
Coexistence | A dual-run/coexistence period (minimum 6–12 months) is assumed between legacy and new platforms.
Cutover Strategy | Migration will follow controlled cutover by capability and queue, not a single enterprise-wide cutover.
Language Support | Multi-language support (especially EMEA) will be implemented during later phases.
Reporting | Reporting and analytics will be consolidated progressively using NICE CXone and existing data sources.
SLA Management | Existing SLAs will be maintained during transition with no disruption to customer operations.

## 6.0 Pricing
6.0 Pricing
All pricing in USD, exclusive of taxes. Four sections: (1) rate card for recurring operational costs by service and geography; (2) Fixed Fee Pricing; (3) One-time transition, Upfront Investments and Implementation costs; (4) Pricing Assumptions; (5) Productivity Assumptions. State all assumptions clearly. Itemize by service and geography throughout.
6.1 Rate Card — Recurring Operations
Provide your rate card for all recurring operational services. Price each sub-service by geography. Assume the unit is in hours. Where you cannot price a line item, state 'Included' or 'N/A' and explain in Assumptions.
|  | USA | Canada | Philippines | Dominican Republic | India | UK | Netherlands | Germany | Philippines | Bulgaria | India
Service | Sub Service | North America — Onshore | North America — Nearshore | North America — Offshore | North America — Offshore | North America — Offshore | EMEA — Onshore | EMEA — Nearshore | EMEA — Nearshore | EMEA — Offshore | EMEA — Offshore | EMEA — Offshore
|  | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($) | Price/Unit ($)
Tier 1 Customer Service | IVR | 49.61 | 36.2389 |  |  | 9.5802 |  | 58.5987 |  |  | 38.0407
Multilingual
| Live Agent | 49.61 | 36.2389 | 13.9194 | 15.3825 |  | 42.628 | 58.5987 | 63.7177 | 13.9194 | 38.0407
| Loyalty | 49.61 |  | 13.9194 | 15.3825
Lost/Stolen
| After hours | 49.61 |  |  |  | 9.5802
Tier 2 Risk Mitigation | Fraud Detection | 53.24 | 37.1422 | 14.8136 | 16.4518 |  | 48.6832 | 86.0563 | 64.5634 | 14.8136 | 39.3685
Fraud Investigation
| Fraud Strategy | 53.24 |  | 14.8136
Fraud Consulting
| Collections | 53.24 |  | 14.8136 |  |  |  |  | 64.5634 |  | 39.3685
Skip Tracing
| Disputes & Chargebacks | 53.24 | 37.1422 | 14.8136 |  |  | 48.6832 | 86.0563 | 64.5634 | 14.8136 | 39.3685
Risk Call Center
Credit
Back Office | Imaging
Copy Requests
Correspondence
Application Processing
Credit Bureau Updates
Returned Mail
Card Destruction
| Account Maintenance | 60.5 |  |  |  | 9.0341 | 56.8317 | 76.7263 |  |  | 40.8634 | 9.0341
Accounting & Settlement
6.2 Annual Cost Escalation by Country
State your assumed annual COLA percentage by country. Must be consistent with your rate card and fixed fee submissions.
Annual COLA Assumption | %
United States | 2.5%
Canada | 2.5%
Philippines | 4%
United Kingdom | 2.5%
Netherlands | 2.5%
Germany | 2.5%
Bulgaria | 2.5%
India | 4%
Dominican Republic | 4%
6.3 Fixed Fee Pricing
Provide quarterly fixed fees for front office, back office, and vendor-funded technology credits over the contract term. Must reconcile to Tab 4.0 and Section 6.1.
Service | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5
($M) | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Fixed Fee — For Front Office Operations
Fixed Fee — For Back Office Operations
Vendor-Funded Technology Investment / Implementation Credit | 0.37769 | 0.37769 | 0.37769 | 0.37769 | 3.7307 | 3.7307 | 3.7307 | 3.7307 | 2.3041 | 2.3041 | 2.3041 | 2.3041 | 2.3041 | 2.3041 | 2.3041 | 2.3041 | 2.3041 | 2.3041 | 2.3041 | 2.3041
6.4 One-Time Transition, Upfront Investments & Implementation Costs
List all one-time costs. Itemize by cost type and geography. Clearly distinguish vendor-funded investment from costs borne by FIS.
Cost Type | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5
Examples Below | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Set up Cost - Transition costs | Year 1 Q1: 0.23994
Rebadging / HR Transition Costs - Onboarding
Technology Overlay Integration
Technology Overlay Licensing
Technology Migration
Training
Dual Run
Up front Investments
In Year Discounts
6.5 Upfront Investment Conditions
For each condition, confirm whether it applies to your proposed investment and provide the required threshold or value.
Conditions for receiving one-time vendor cash payment | Year 1 Q1: Is this a condition (Y/N); Year 1 Q2: Required value
Is there a minimum volume requirement for NA scope of work, if yes provide % of total volume | Year 1 Q2: TBD
Is there a minimum volume requirement for EMEA scope of work, if yes provide % of total volume | Year 1 Q2: TBD
Is partial or complete rebadging (specified in section 3) a pre condition to this upfront investment? | Year 1 Q2: TBD
Minimum contract duration, if yes provide number of years | Year 1 Q2: TBD
Other: <pls add additional rows as necessary> | Year 1 Q2: TBD
6.6 Pricing Assumptions
List all assumptions underpinning your pricing across all three sections above. Include: FTE volume assumptions, indexation methodology, how you have structured fixed vs. variable components, your fixed fee breakdown (front-office vs. back-office), any vendor-funded technology investment or implementation credit, and any deal sweeteners, transition credits, or gain-share mechanisms proposed.
# | Year 1 Q1: Assumptions
1 | Year 1 Q1: Billing Methodology : Our preferred model is Total Cost of Ownership. We have also provided the hourly rate as requested in the RFP
2 | Year 1 Q1: The rates are all inclusive rates - fixed for first 5 years and YoY COLA for Y6 & Y7 is considered at rates applicable for each Geo
3 | Year 1 Q1: For the Rate card - all frontline resources and support roles have been considered as billable
4 | Year 1 Q1: Deal Term is assumed to be 7 Years (5 years + 1 + 1 renewal)
5 | Year 1 Q1: For pricing purposes we have assumed WAH for US & Canada and B&M for rest of the Geos
6 | Year 1 Q1: Commercial are subject to and contingent upon the outcome of due diligence
7 | Year 1 Q1: Prices quoted are exclusive of all GST, sales, service, excise, consumption, lease, use and other value added taxes
8 | Year 1 Q1: Baseline in TCO model provided is based on the 2026 budgets shared by FIS (TSYS). The remaining years are adjusted with 2.5% YoY COLA increase
9 | Year 1 Q1: Resource cost for region is aligned with the 2026 budget and is based on our estimate for each of the locations within a specific region. The resource cost shall be revised once we get detailed HR roster
10 | Year 1 Q1: All liabilities related to rebadged resources until the point of transfer shall reside with FIS (TSYS) and are subject to TUPE and ARD requirements
11 | Year 1 Q1: Assumed that Sutherland will takes over the leased facilities of FIS (TSYS) in EMEA region along with its Tech & Non-Tech assets (Laptops, furnitures & fittings, etc) at written down value where applicable. Facility lease rentals considered as per 2026 budget numbers as part of RFP.
12 | Year 1 Q1: In the event these dependencies are delayed or not achieved as assumed, the transformation timelines, benefits realization, and associated commercial assumptions may require review and mutual alignment
13 | Year 1 Q1: In Appendix B, table 6.2 Annual Cost Escalation by Country - The Hourly rates are inclusive of COLA for Y1-Y5. Geo wise COLA is applicable from Y6 onwards which is updated in Section 6.2
Section 6.7 — 5-Year Financial Summary
Summarize the total cost of the proposed engagement over the contract term. All figures in USD millions. This table will be used to calculate Total Contract Value and net savings versus FIS's cost baseline. Figures must be consistent with pricing submitted in Sections 6.1–6.3 above. Efficiency savings figures in this table must reconcile directly to commitments stated in Tab 5.0 Technology Solution. Any discrepancy between this table and Tab 5.0 must be explained in Section 6.4 Pricing Assumptions.
| Year 1 Q1: Year 1; Year 2 Q1: Year 2; Year 3 Q1: Year 3; Year 4 Q1: Year 4; Year 5 Q1: Year 5 | Year 6 |  |  |  | Year 7
Cost Category | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
North America Direct Costs | 25.6755 | 25.6755 | 25.6755 | 25.6755 | 13.3289 | 13.3289 | 13.3289 | 13.3289 | 9.8067 | 9.8067 | 9.8067 | 9.8067 | 9.2912 | 9.2912 | 9.2912 | 9.2912 | 9.0144 | 9.0144 | 9.0144 | 9.0144 | 8.6828 | 8.6828 | 8.6828 | 8.6828 | 8.4877 | 8.4877 | 8.4877 | 8.4877
EMEA Direct Costs | 25.0253 | 25.0253 | 25.0253 | 25.0253 | 18.4375 | 18.4375 | 18.4375 | 18.4375 | 10.3563 | 10.3563 | 10.3563 | 10.3563 | 9.6524 | 9.6524 | 9.6524 | 9.6524 | 9.327 | 9.327 | 9.327 | 9.327 | 8.9205 | 8.9205 | 8.9205 | 8.9205 | 8.6959 | 8.6959 | 8.6959 | 8.6959
Total Annual Cost ($M) | 50.7008 | 50.7008 | 50.7008 | 50.7008 | 31.7664 | 31.7664 | 31.7664 | 31.7664 | 20.1629 | 20.1629 | 20.1629 | 20.1629 | 18.9436 | 18.9436 | 18.9436 | 18.9436 | 18.3414 | 18.3414 | 18.3414 | 18.3414 | 17.6033 | 17.6033 | 17.6033 | 17.6033 | 17.1836 | 17.1836 | 17.1836 | 17.1836
Savings (%) | 0.1948% | 0.1948% | 0.1948% | 0.1948% | 30.29% | 30.29% | 30.29% | 30.29% | 46.78% | 46.78% | 46.78% | 46.78% | 51.22% | 51.22% | 51.22% | 51.22% | 53.92% | 53.92% | 53.92% | 53.92% | 56.85% | 56.85% | 56.85% | 56.85% | 58.91% | 58.91% | 58.91% | 58.91%

## 7.0 Client Migration
7.0 Client Migration Planning
A de-identified client dataset will be provided alongside this RFP. A migration wave is a defined group of clients that will transition to the new operating model together, with a shared go-live date and dual-run period. (1) Using the supplemental data provided, please architect waves of clients/queues/locations/ regions and articulate the rationale. (2) Use the Wave Summary below to plot your wave against time. (3) Define a RACI for the Client Migration efforts.
7.1 Client Migration Wave Design
Part 1 — Wave Composition: For each wave, list which client cohorts are included, explaining what criteria drove the grouping; for all clients, specify which client is mapped to each wave. FIS has intentionally not prescribed a wave structure or grouping methodology. We expect vendors to analyze the client dataset provided and propose the wave design they believe is most operationally sound for an engagement of this complexity. There is no correct number of waves. Responses that demonstrate genuine analytical thinking about client risk, regulatory complexity, volume sequencing, and transition readiness will be evaluated more favorably than generic frameworks.
Wave # | Client Name | Wave Assignment Rationale | Key Migration Risks & Mitigations | Wave Type | Location | Start Date | End Date | FTEs | Number of classes
Wave 1 | All clients supported from USA & Philippines | Commence Transition with backfill classes assuming 5% fallout from Rebadge activity | 5% fallout from incumbent team post announcement of Rebadge activity. Sutherland will ensure backfill resources are hired and ready to support for continuity of operations. | Backfill | India & Philippines | 2026-06-29 | 2026-08-21 | 66 | 11 classes covering all processes
Wave 2 | All clients support from Canada & UK | Commence Transition with backfill classes assuming 5% fallout from Rebadge activity | 5% fallout from incumbent team post announcement of Rebadge activity. Sutherland will ensure backfill resources are hired and ready to support for continuity of operations. | Backfill | India & Philippines | 2026-07-06 | 2026-08-28 | 50 | 5 classes covering all processes
Wave 3 | All clients support from Germany & Netherlands | Commence Transition with backfill classes assuming 5% fallout from Rebadge activity | 5% fallout from incumbent team post announcement of Rebadge activity. Sutherland will ensure backfill resources are hired and ready to support for continuity of operations. | Backfill | India, Philippines & Bulgaria | 2026-07-20 | 2026-09-04 | 18 | 6 classes covering all processes
Wave 4 | All clients supported from USA & Philippines | Rebadge activity to be completed prior to any migration to offshore locations | Loss of key personnel and tribal knowledge once the rebadging annoucement has been made. Sutherland in partnership with FIS will manage the communication and change well to mitigate any fallout | Rebadge | Existing sites in USA & Philippines | 2026-08-17 | 2026-08-28 | 1160 | Rebadging to be done in 3-4 batches across 2 weeks
Wave 5 | All clients support from Canada & UK | Rebadge activity to be completed prior to any migration to offshore locations | Loss of key personnel and tribal knowledge once the rebadging annoucement has been made. Sutherland in partnership with FIS will manage the communication and change well to mitigate any fallout | Rebadge | Existing sites in Canada & UK | 2026-08-31 | 2026-09-04 | 766 | Rebadging to be done in 2-3 batches across 1 week
Wave 6 | All clients support from Germany & Netherlands | Rebadge activity to be completed prior to any migration to offshore locations | Loss of key personnel and tribal knowledge once the rebadging annoucement has been made. Sutherland in partnership with FIS will manage the communication and change well to mitigate any fallout | Rebadge | Existing sites in Germany & Netherlands | 2026-09-07 | 2026-09-11 | 340 | Rebadging to be done in 2-3 batches across 1 week
Wave 7 | Accounting- All clients supported from USA | Kick off right shoring activity with a process with low headcount | Low risk. Sutherland will ensure the knowledge transfer is effective between the onsite & offshore teams | Right shoring | India | 2026-09-14 | 2026-11-06 | 8 | 1 class
Wave 8 | Backoffice- All clients supported from USA | Migrate the rule based repeatable tasks to offshore location | Low risk. Sutherland will ensure the knowledge transfer is effective between the onsite & offshore teams | Right shoring | India | 2026-10-12 | 2027-01-15 | 182 | 4 classes
Wave 9 | IVR/Tech- All clients supported from USA | Complete migration to India with the Tech processes. | Low risk. Sutherland will ensure the knowledge transfer is effective between the onsite & offshore teams | Right shoring | India | 2026-12-07 | 2027-01-29 | 5 | 1 class
Wave 10 | Off Phone- All clients supported from USA | Complete migration to India with the Off Phone activity | Low risk. Sutherland will ensure the knowledge transfer is effective between the onsite & offshore teams | Right shoring | India | 2026-12-07 | 2027-01-29 | 24 | 1 class
Wave 11 | Customer Service- All clients supported from USA | Kick off right shoring activity in Philippines with the simplest process | Impact in customer experience post migration to the new team. Sutherland will ensure the right resources are hired to deliver quality service | Right shoring | Philippines, Dominican Republic | 2026-10-12 | 2027-01-29 | 272 | 12 classes
Wave 12 | Collections- All clients supported from USA | Migrate the low volume process at the same time as the Customer Service process | Impact in customer experience post migration to the new team. Sutherland will ensure the right resources are hired to deliver quality service | Right shoring | Philippines | 2026-10-12 | 2026-12-04 | 9 | 1 class
Wave 13 | Loyalty- All clients supported from USA & Canada | Migrate the relatively simpler Loyalty process post migration of Customer Service | Impact in customer experience post migration to the new team. Sutherland will ensure the right resources are hired to deliver quality service | Right shoring | Philippines, Dominican Republic | 2026-12-21 | 2027-03-12 | 92 | 5 classes
Wave 14 | Disputes- All clients supported from USA & Canada | Post migration of CS & Loyalty, commence migration of more complex processes | Loss of knowledge and continuity of cases while migrating between teams. Sutherland will ensure the documentation and case management is robust. | Right shoring | Philippines | 2027-01-25 | 2027-04-16 | 90 | 5 classes
Wave 15 | Fraud Inbound, Outbound & Strategy- All clients supported from USA | Migrate the most complex process last | Loss of knowledge and continuity of cases while migrating between teams. Sutherland will ensure the documentation and case management is robust. | Right shoring | Philippines, Dominican Republic | 2027-03-01 | 2027-08-20 | 459 | 21 classes
Wave 16 | Back office- All clients supported from UK, Germany & Netherlands | Backfill the rule based repeatable tasks at offshore locations | Low risk. Hire and train backfill resources in anticipation of attrition at onshore locations | Backfill | India | 2026-11-09 | 2028-03-03 | 25.04 | 5 classes
Wave 17 | Customer Service- All clients supported from UK, Germany & Netherlands | Backfill at offshore location based on natural attrition at onshore locations | Low risk. Hire and train backfill resources in anticipation of attrition at onshore locations | Backfill | Philippines & Bulgaria | 2026-10-12 | 2028-04-21 | 316.56 | 18 classes
Wave 18 | Dispute- All clients supported from UK, Germany & Netherlands | Backfill at offshore location based on natural attrition at onshore locations | Low risk. Hire and train backfill resources in anticipation of attrition at onshore locations | Backfill | Philippines & Bulgaria | 2026-10-12 | 2028-03-17 | 122.12 | 11 classes
Wave 19 | Fraud- All clients supported from UK, Germany & Netherlands | Backfill at offshore location based on natural attrition at onshore locations | Low risk. Hire and train backfill resources in anticipation of attrition at onshore locations | Backfill | Philippines & Bulgaria | 2026-10-19 | 2028-04-14 | 280.04 | 15 classes
Wave 20 | Collections- All clients supported from UK, Germany & Netherlands | Backfill at offshore location based on natural attrition at onshore locations | Low risk. Hire and train backfill resources in anticipation of attrition at onshore locations | Backfill | Bulgaria | 2026-10-12 | 2026-12-03 | 0.76 | 1 class
Wave 21 | IVR/Tech- All clients supported from UK, Germany & Netherlands | Backfill at offshore location based on natural attrition at onshore locations | Low risk. Hire and train backfill resources in anticipation of attrition at onshore locations | Backfill | Bulgaria | 2026-11-02 | 2028-03-03 | 6.84 | 4 classes
Part 2 — Wave Timeline: For each wave, state the proposed start date, go-live date, and dual-run duration. Please visually differentiate between the migration and dual run periods, if applicable. FIS has intentionally not prescribed a wave structure or grouping methodology. We expect vendors to analyze the client dataset provided and propose the wave design they believe is most operationally sound for an engagement of this complexity. There is no correct number of waves. Responses that demonstrate genuine analytical thinking about client risk, regulatory complexity, volume sequencing, and transition readiness will be evaluated more favorably than generic frameworks.
Wave | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Wave 1- Backfill US & PH rebadge (Double run) | Year 1 Q2: Start 29 Jun; Year 1 Q3: End 21 Aug
Wave 2- Backfill CA & UK rebadge (Double run) | Year 1 Q3: Start 6 Jul - End 28 Aug
Wave 3- Backfill GR & NE rebadge (Double run) | Year 1 Q3: Start 20 Jul- End 4 Sep
Wave 4- Rebadge US & PH | Year 1 Q3: Start 17 Aug- End 28 Aug
Wave 5- Rebadge CA & UK | Year 1 Q3: Start 31 Aug- End 4 Sep
Wave 6- Rebadge GR & NE | Year 1 Q3: Start 7 Sep- End 11 Sep
Wave 7- Right shoring- US Accounting | Year 1 Q3: Start 14 Sep; Year 1 Q4: End 6 Nov
Wave 8- Right shoring- US Backoffice | Year 1 Q4: Start 12 Oct; Year 2 Q1: End 15 Jan
Wave 9- Right shoring- US IVR/Tech | Year 1 Q4: Start 7 Dec; Year 2 Q1: End 29 Jan
Wave 10- Right shoring- US Off Phone | Year 1 Q4: Start 7 Dec; Year 2 Q1: End 29 Jan
Wave 11- Right shoring- US Customer Service | Year 1 Q4: Start 12 Oct; Year 2 Q1: End 29 Jan
Wave 12- Right shoring- US Collections | Year 1 Q4: Start 12 Oct- End 4 Dec
Wave 13- Right shoring- US & CA Loyalty | Year 1 Q4: Start 21 Dec; Year 2 Q1: End 12 Mar
Wave 14- Right shoring- US & CA disputes | Year 2 Q1: Start 25 Jan; Year 2 Q2: End 16 Apr
Wave 15- Right shoring- US Fraud | Year 2 Q1: Start 1 Mar; Year 2 Q3: End 20 Aug
Wave 16- Backfill- EU Backoffice | Year 1 Q4: Start 9 Nov; Year 3 Q1: End 3 Mar
Wave 17- Backfill- EU Customer Service | Year 1 Q4: Start 12 Oct; Year 3 Q2: End 21 Apr
Wave 18- Backfill- EU Disputes | Year 1 Q4: Start 12 Oct; Year 3 Q1: End 17 Mar
Wave 19- Backfill- EU Fraud | Year 1 Q4: Start 19 Oct; Year 3 Q2: End 14 Apr
Wave 20- Backfill- EU Collections | Year 1 Q4: Start 12 Oct- End 3 Dec
Wave 21- Backfill- EU IVR/Tech | Year 1 Q4: Start 2 Nov; Year 3 Q1: End 3 Mar
7.3 Client Migration Responsibility Matrix | bar: Year 1 Q1 to Year 1 Q2
Populate a RACI of what TSYS/FIS will be responsible for and what you will be responsible for; FIS has not pre-populated this RACI. Vendors are expected to propose the full activity list they believe is required to execute a migration of this scale, and to assign responsibility accordingly. Responses should reflect your actual delivery methodology — not a generic RACI template. Activities should cover at minimum: client readiness, knowledge transfer, dual-run management, cutover approval, stabilization, and hypercare exit. Add rows as needed.
Activity | Year 1 Q1: TSYS/FIS; Year 1 Q2: Sutherland; Year 1 Q3: Remarks
Mobilization | bar: Year 1 Q1 to Year 1 Q3
Provide operational due diligence inputs (processes, volumes, contracts) | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: FIS / TSYS provides current-state data
Provide workforce data (salary, compensation, benefits, leave, BGV, certifications, PIP, disciplinary records) | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: Subject to legal and privacy requirements
Provide site details, lease data, facilities information, and seat capacity | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: Current-state site baseline
Provide technology asset inventory, asset condition, license inventory, and tool landscape | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: Hardware, software, licenses, support contracts
Provide SME support for discovery sessions and solution validation | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: Includes client and operations discovery
Lead Transition Governance and PMO | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Sutherland owns overall transition governance
Build transition plan, wave plan, and integrated milestone plan | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Includes sub-waves and geo sequencing
Lead communication planning and execution for transition | Year 1 Q1: Yes; Year 1 Q2: Yes; Year 1 Q3: Includes employee and stakeholder communications
Discuss with clients migration/rightshoring sign off and Sutherland to create the rightshoring solution | Year 1 Q1: Yes; Year 1 Q2: Yes; Year 1 Q3: Sutherland owns pursuit and migration planning in partnership with FIS
Participate in client discovery sessions | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: FIS / TSYS supports with current-state context
Lead client discovery sessions and solution workshops | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Sutherland owns workshops and future-state design
HR / Rebadge | bar: Year 1 Q1 to Year 1 Q3
Lead all rebadge strategy and planning | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: All rebadge activities sit with Sutherland
Execute employee rebadging | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Offer letters, contracting, onboarding, transition logistics
Lead payroll migration and benefits transition | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Includes validations and cutover readiness
Lead retention, attrition, and employee engagement actions | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Includes retention plans for critical talent
Workforce Continuity
Lead backfill hiring plan | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Designed to offset projected attrition
Execute backfill hiring and training before rebadge | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Pre-rebadge KT for continuity coverage
Lead right-shoring strategy and execution | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Offshore, onshore, nearshore target model
Provide SME support for right-shoring and offshore transition | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: FIS / TSYS enables knowledge continuity
Knowledge Transfer
Build KT plan and certification criteria | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Sutherland defines readiness gates
Deliver KT sessions for backfill classes | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: FIS / TSYS SMEs transfer knowledge
Validate KT completion and certify readiness | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Entry gate to reverse shadow
Provide SOPs, runbooks, process maps, and control documentation | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: Complete and current documentation set
Technology
Provision access to current tools, systems, and environments | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: Includes connectivity, application, and platform access
Provide technology architecture details and integration dependencies | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: Current-state technical baseline
Provide asset inventory and condition assessment | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: End-user computing and site assets
Provide software license and entitlement details | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: License status and transfer constraints
Lead target tool setup, environment configuration, and migration readiness | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Sutherland target-state setup
Lead technology transition planning and cutover coordination | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: End-to-end technology workplan
Lead site transition planning and operational readiness | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Site readiness for ongoing operations
Run shadow operations | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: FIS / TSYS operates while Sutherland observes
Run reverse shadow operations | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Sutherland operates while FIS / TSYS supervises
Parallel Run | bar: Year 1 Q1 to Year 1 Q3
Run parallel operations of backfill classes | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Sutherland owns execution during parallel run
Provide oversight and support during parallel run | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: FIS / TSYS supports issue resolution
Lead SLA tracking, performance reporting, and issue management | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Daily operational governance
Go-Live
Lead go-live readiness assessment and cutover execution | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Final go / no-go ownership
Hypercare | bar: Year 1 Q1 to Year 1 Q3
Provide stabilization oversight and SME support during hypercare | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: Time-bound support after go-live
Lead hypercare management and service stabilization | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Sutherland owns steady-state ramp
Stabilization | bar: Year 1 Q1 to Year 1 Q3
Lead final acceptance, transition closure, and steady-state handoff | Year 1 Q1: No; Year 1 Q2: Yes; Year 1 Q3: Formal closeout of transition program
Exit
Execute disengagement and exit from transitioned scope | Year 1 Q1: Yes; Year 1 Q2: No; Year 1 Q3: FIS / TSYS exits retained activities
As mentioned in the response to questions, Sutherland has not answered the below table. | bar: Year 1 Q1 to Year 2 Q1
7.4 Transformation Assumptions | bar: Year 1 Q1 to Year 2 Q1
At a per client level, what is the commitment from the vendor on offshore to onshore mix, consequent labor arbitrage %, cost reduction from AI & Digital Overlays, cost reduction from Productivity gains
Client Name | Year 1 Q1: Offshore to Onshore Mix; Year 1 Q2: Consequent Labor Arbitrage %; Year 1 Q3: Cost Reduction from AI & Digital Overlays %; Year 1 Q4: Cost Reduction from Productivity Gains %; Year 2 Q1: Commitment to Certainty of Cost Savings as a %
US & Canada Clients Clients | Year 1 Q1: Vendor to provide; Year 1 Q2: Vendor to provide; Year 1 Q3: Vendor to provide; Year 1 Q4: Vendor to provide; Year 2 Q1: Vendor to provide
Netherlands Clients | bar: Year 1 Q1 to Year 1 Q2
Germany Clients | bar: Year 1 Q1 to Year 2 Q1
United Kingdom Clients | bar: Year 1 Q1 to Year 2 Q1
Philippines Clients | bar: Year 1 Q1 to Year 2 Q1

## 8.0 Regulatory Compliance
8.0 Regulatory Compliance
For each requirement listed in Column C, provide your response in Column D. Responses should be specific to this engagement and the regulatory environments in scope. Where certifications or formal frameworks apply, state them.
8.1 Transformation Assumptions
Regulatory Area | Specific Requirement | Vendor Response — How Your Solution Meets This Requirement
4th Party Outsourcing | Disclose all sub-contractors by name, location, and scope. Confirm SLA flow-down and FIS audit rights over all 4th parties. | For this engagement, we may plan to use multiple sub-contractors. For e.g., we plan to use Uniphore as a specialized sub contractor to provide the unified desktop and real time agent assist solution that underpins our digital transformation and CX optimization objectives. Uniphore’s platform will be used to deliver unified agent workflows and real time guidance from approved locations, while all core service delivery, governance, and client facing roles remain with Sutherland as the prime contractor. We are utilizing Uniphore as a sub-contractor to provide AI services to FIS already. There maybe a need to evaluate possible use of additional sub-contractors to deliver services in EMEA region. We also constantly evaluate best in industry AI solutions to bring the best of global AI tools and technology to deliver the transformation solutions we are proposing as part of our response. Should any additional sub contractors be required as the engagement evolves, Sutherland will notify the client in advance, provide full details of scope, location, and controls, and obtain the client’s prior written approval before onboarding. 2. SLA flow down mechanism All SLAs, security, confidentiality, data protection, and regulatory obligations agreed with the client are contractually flowed down to our sub-contractors through back to back agreements that mirror the requirements in the prime contract. We operate a single integrated SLA and governance framework in which our sub-contractors performance is monitored alongside Sutherland’s operations via common dashboards and review forums, with defined remediation actions and the right to invoke service credits or adjust or terminate the sub contract arrangement in the event of persistent under performance. In summary, overall performance of this engagement (including anything sent to sub-contractor) will be the responsibility of Sutherland. 3. Client audit rights over sub contractors The client will retain full audit and inspection rights, as defined in the master services agreement, over material sub contractors used in delivering TMS services, including our sub-contractors. These rights (such as access to relevant records, processes, and control evidence, subject to reasonable notice and confidentiality) are embedded in our contract with our partner sub-contractors to ensure that the client’s and regulators’ audit and oversight requirements can be met seamlessly across the delivery chain.
4th Party Outsourcing | Describe your internal governance model for monitoring sub-contractor performance and compliance. | Sutherland uses a standardized third‑party risk and vendor governance framework to oversee all sub‑contractors supporting our services. Sub‑contractors are risk‑tiered, with clear ownership, SLAs/KPIs aligned to client commitments, and regular performance reviews and scorecards. Compliance is monitored through periodic risk assessments, security and data‑protection checks, incident reporting and remediation, and participation in internal and client/regulatory audits, with contractual remedies available where performance or compliance falls below agreed thresholds.
Offshoring & Nearshoring | Confirm cardholder data will not leave approved jurisdictions without explicit client consent. Describe data residency controls. | To confirm, cardholder data (CHD) is strictly confined to approved jurisdictions through a combination of geographic pinning and rigorous technical egress filters, ensuring no data crosses borders without explicit client consent. This is enforced by hosting sensitive workloads in regional "silos"—physically isolated data centers—where infrastructure-as-code policies block the provisioning of storage in unauthorized territories. To prevent accidental or malicious transfers, Data Loss Prevention (DLP) tools and geofencing are deployed to monitor and intercept outbound traffic containing Primary Account Numbers (PANs). These residency controls are validated through continuous automated data discovery and annual audits to maintain compliance with both regional legal mandates and PCI DSS standards
Offshoring & Nearshoring | Describe the regulatory notification process before offshoring commences (e.g. FCA Principal 11 notification — UK; WARN Act — US). Confirm who is responsible for filings. | Sutherland would be responsible for regulatory notification process (provided we have completed rebadging and site take over processes). Regulated firms in the UK must adhere to strict notification requirements under the Financial Services and Markets Act 2000 (FSMA), FCA Principles for Businesses (Principle 11), and Prudential Regulation Authority (PRA) rules. Process: Materiality Assessment: Before notifying, firms must determine if the offshoring arrangement is "material" (i.e., its failure would cause intolerable harm to clients, the firm, or the stability of the UK financial system). Advance Notification: Firms must give advance notice to the FCA or PRA of any proposal to enter into a material outsourcing arrangement or significant changes to existing arrangements. Principle 11 Notification: Deals with regulators "in an open and cooperative way" and includes disclosing anything the regulator would reasonably expect notice of. Responsible Party: The governing body and senior management of the authorized UK firm. The federal Worker Adjustment and Retraining Notification (WARN) Act requires employers to provide notice before massive layoffs or plant closures caused by moving operations offshore. Process: Notification Requirements: Covered employers must provide 60 calendar days' advance written notice of a plant closing or mass layoff to employees (or their representatives/unions), the state's rapid-response dislocated worker unit, and the chief elected official of the local government. Triggering Events: A plant closing affecting 50 or more employees at a single site, or a mass layoff involving 500+ employees, or 50–499 employees if they make up 33% of the workforce. Responsible Party: The employer (parent company or subsidiary), generally determined by the entity managing the facility and employment relationships.
Offshoring & Nearshoring | Describe your approach to clients with explicit offshore restrictions in their current TMS contracts. | There are several benefits of offshoring and nearshoring for clients in terms of cost, productivity and improcing digitization of processes, resulting in a better end-customer experience. Sutherland would bring in a team of experts in regulatory compliance, legal, global operations leader, BFS leadership, transition & transformation and commercial constuct experts to design a strategy to address key issues and challenges and pave the way for a seamless transtion to an offshore environment. We have done this successfully for clients in Payments and Cards issuing business, working with our clients to help get approvals from their clients to offshore. We will bring this experience to FIS to help enable and drive this faster. Sutherland would propose to jointly review all such contracts where offshoring restrictions are present, to understand what considerations have gone into taking that view. Once we jointly analyze, we can build a commong strategy to address the previous and ensuing concerns and build a joint "Go to Market" plan to take them to these clients. We would leverage credible proof points, artefacts and other collaterals to impress upon them and make them agree to consider the offshoring option from operational, legal and regulatory compliance aspect.
Customer PII, GDPR & Privacy | GDPR — confirm DPA agreements, data processor obligations, cross-border transfer mechanisms, and breach notification procedures (including SLA to notify FIS). | Sutherland agrees to execute a mutually acceptable DPA covering all applicable data protection obligations across relevant privacy regulations globally. For cross-border transfers, Sutherland holds EU-US Data Privacy Framework certification including the UK and Swiss Extensions, is certified under both APEC CBPR and the Global CBPR Framework, and SCCs will be incorporated into the DPA. Sutherland maintains a robust breach management process and will strictly adhere to the agreed notification SLA to FIS as set out in the MSA/DPA.
Customer PII, GDPR & Privacy | US cardholder data — confirm CCPA compliance and your approach to state-level privacy law variation. | Sutherland's Privacy Information Management System (PIMS) is led by a designated Data Protection Officer (DPO) and incorporates the guidelines and controls required to meet applicable regulatory obligations. Sutherland’s compliance framework includes regular education and training, monitoring and auditing, and enforcement of compliance policies and procedures. The company’s privacy program includes administrative, physical, and electronic controls over confidential information, and specific policies regarding individuals’ rights to access, amend, and restrict the use of their personal information. Sutherland’s legal and compliance teams continuously monitor legislative and regulatory changes, including state-level privacy law variations, to ensure ongoing compliance and seamless implementation of necessary changes. Sutherland is also certified under ISO 27001 and ISO 27701, further demonstrating its commitment to robust data security and privacy management. These measures collectively ensure that Sutherland’s handling of US cardholder data is compliant with the CCPA and adaptable to state-level privacy law variations.
Customer PII, GDPR & Privacy | PCI DSS — confirm current certification level, scope, and most recent assessment date. | The current PCI DSS certification was attained on April 19, 2023, and applies to credit card lines of business. Sutherland has maintained PCI DSS compliance since 2010. The scope of certification is for credit card processing activities, supported by the implementation of Sentinel Secure, an innovative payment gateway ensuring 100 percent PCI compliance and agent fraud prevention. Details regarding the most recent assessment date are provided as April 19, 2023. Regarding data ownership and portability, the context does not explicitly confirm that FIS retains full ownership and portability of all data at all times, nor does it describe the mechanism for full data extraction upon contract exit.
InfoSec & Data Governance | Confirm FIS retains full ownership and portability of all data at all times. Describe the mechanism for full data extraction upon contract exit. | Sutherland confirms that FIS always retains full ownership of all data. Sutherland acts solely as a data processor/service provider, with no rights, title, or interest in client data beyond what is required to deliver contracted services. These controls are governed under our ISO 27001 (ISMS), ISO 27701 (PIMS), PCI DSS, and SOC 2 compliant frameworks. • Data Ownership Assurance: All data, including cardholder data (CHD), personal data, and associated metadata, is contractually recognized as the exclusive property of FIS. Sutherland enforces strict data handling, classification, and access controls to ensure data is processed only for authorized business purposes and in accordance with client instructions. • Data Portability & Accessibility: Sutherland ensures that client data is maintained in structured, commonly used, and machine-readable formats to support seamless portability. Data is logically segregated per client, enabling efficient extraction without commingling with other client datasets. • Data Extraction Mechanism (Contract Exit): Upon contract termination or upon request, Sutherland supports full data extraction through secure and controlled processes, including: o Provision of data exports in agreed formats (e.g., CSV, encrypted databases, or other client-specified formats). o Secure transfer mechanisms such as SFTP, encrypted storage media, or dedicated secure file exchange platforms. o Validation and reconciliation of extracted data to ensure completeness and integrity. o Defined timelines and SLAs to support timely data handover as per contractual agreements. • Security During Data Transfer: All data extraction and transfer activities are secured using strong encryption (in transit and at rest) in alignment with PCI DSS and industry best practices. Access to extraction processes is restricted, logged, and monitored to prevent unauthorized disclosure. • Data Retention & Secure Disposal: Following successful data handover and client confirmation, Sutherland performs secure data deletion in accordance with contractual requirements and regulatory standards. Certified data destruction methods are applied, and certificates of destruction are provided upon request. • Audit & Compliance Assurance: The entire process is governed by documented procedures and subject to internal and external audits under ISO 27001, ISO 27701, PCI DSS, and SOC 2 frameworks, ensuring transparency, accountability, and compliance. These measures ensure that FIS maintains continuous ownership and control of its data, with assured portability and secure, complete extraction upon contract exit.
InfoSec & Data Governance | Confirm logical and/or physical segregation of cardholder data across different FIS clients. | Sutherland confirms that robust logical and physical segregation controls are implemented to ensure strict isolation of cardholder data (CHD) . These controls are aligned with our ISO 27001, ISO 27701, and SOC 2 certified information security and privacy frameworks. • Logical Segregation: Client environments are logically segregated through secure network architecture, including VLAN segmentation, firewalls, and access control mechanisms. Role-Based Access Control (RBAC) and least privilege principles are enforced to ensure that access to cardholder data is restricted to authorized personnel on a need-to-know basis. Dedicated application instances and database schemas further ensure tenant-level data isolation. • Physical Segregation: Where applicable, physical segregation is maintained through controlled access to data center facilities, restricted zones, and dedicated infrastructure for specific client requirements. Data centers are secured with multi-layered physical security controls, including biometric access, surveillance, and 24/7 monitoring. • Data Protection Controls: If stored in Sutherland environment Cardholder data is protected using strong encryption (both at rest and in transit), masking, and tokenization techniques where required. Data handling processes are governed by strict policies aligned with PCI DSS requirements.
InfoSec & Data Governance | Describe security controls for remote/WFH agents handling cardholder data (screen capture, device management, network security, print restrictions). | If the Card Data is stored in environment, Sutherland enforces stringent security controls for remote/WFH agents handling cardholder data (CHD), aligned with our ISO 27001, ISO 27701, PCI DSS, and SOC 2 compliance frameworks. These controls are designed to ensure confidentiality, integrity, and secure processing of sensitive payment information in remote environments. • Secure Access & Environment Controls: WFH access for CHD processing is enabled only through controlled, risk-assessed environments and subject to client approval where required. Access is provisioned via secure Virtual Desktop Infrastructure (VDI) or hardened remote access solutions with Multi-Factor Authentication (MFA). Sessions are fully monitored and restricted to prevent local data storage or data exfiltration. • Screen Capture & Monitoring Controls: Screen capture, recording, and real-time monitoring solutions are implemented in compliance with PCI DSS requirements. Controls include disabling unauthorized screen capture utilities, restricting copy/paste functions, and enabling session recording where contractually required. Data masking and pause-and-resume controls are enforced during sensitive data entry. • Endpoint / Device Management: Only Sutherland-managed and hardened endpoints are permitted for CHD access. Devices are configured with endpoint protection, host-based firewalls, disk encryption, and Data Loss Prevention (DLP) controls. Administrative privileges are restricted, and USB/external media access is disabled. Devices are continuously monitored and patched in line with defined security baselines. • Network Security Controls: Remote connectivity is secured through encrypted VPN tunnels or zero-trust network access (ZTNA) solutions with strong authentication. Network configurations enforce traffic inspection, intrusion detection/prevention, and geo/IP restrictions. Home network requirements are defined and validated, including secure Wi-Fi configurations (WPA2/WPA3) and prohibition of public or unsecured networks. • Print & Data Handling Restrictions: Printing of CHD is strictly prohibited in WFH environments. System-level controls prevent print screen, local printing, and data downloads. Clipboard restrictions, file transfer blocking, and watermarking mechanisms are enforced to prevent unauthorized data capture or sharing. • Policy Enforcement & Awareness: Agents are required to comply with strict clean desk/clear screen policies adapted for WFH, including workspace privacy requirements. Mandatory security and privacy training, including PCI DSS awareness, is completed prior to access provisioning and refreshed periodically. • Monitoring, Logging & Compliance Assurance: All remote sessions are logged and continuously monitored for anomalous activity. Security events are centrally managed via SIEM solutions, with defined incident response procedures. These layered controls ensure that cardholder data handled by remote/WFH agents remains secure, compliant, and protected against unauthorized access, disclosure, or misuse.
Responsibility for Penalties | Who bears liability for regulatory fines resulting from vendor non-compliance? Describe indemnity and remediation framework for client disputes arising from vendor error. | Sutherland is contractually obligated to meet all mandated regulations and maintains robust compliance frameworks, including regular internal and external audits, to ensure adherence to regulatory requirements. In the event of disputes arising from vendor error, Sutherland has, on a very limited basis, indemnified vendors in the past. For example, Sutherland shared reasonable and nominal legal costs with a customer who was sued for alleged infringement related to a third-party software tool used by Sutherland in service delivery. Sutherland reserves the right to enter into further good faith contract negotiations regarding indemnity and other contractual provisions, based on the specifics of each deal. Significant corrective measures and consequence management are part of Sutherland’s policies and procedures in case of any non-adherence to regulatory compliance, supported by regular internal audits and compliance monitoring.
Financial Services — NA | CFPB — describe your compliance program and oversight model for collections, disputes, and customer service operations. | Sutherland's collections, disputes and customer service operations are designed around US consumer lending laws—TCPA, FDCPA, Reg F, UDAAP, SCRA/MLA, FCRA, TILA, CFPB and state-specific rules. Sutherland has developed and maintained a compliance management system (CMS) that is integrated into the overall management strategy of the organization. We take an integrated approach to our CMS that incorporates provisions from both our end and our clients to provide multiple benefits, not just at a strategic level but also at the operational, day-to-day level. The Sutherland Compliance Management System • Establishes its compliance responsibilities • Communicates those responsibilities to employees • Ensures business processes incorporate internal policies for meeting legal requirements • Reviews operations to ensure accountability for meeting assigned responsibilities and legal requirements • Takes corrective action and updates tools, systems, and materials as needed A continuous CMS cycle allows Sutherland to create, maintain, and update the compliance management system so that it is effective in identifying, measuring, monitoring, controlling, and addressing compliance risks to consumers and to your organization.Sutherland Compliance Management System • Licensing, Reporting, Insurance, Taxing Authorities • Regulatory Review – Policy and Procedures • Compliance Training on Policy and Procedures • Internal Audit of the origination practices and LOS System • Self-Testing and Reporting • External Audit - Regulatory Examination State and Federal, HUD • Complaint Management – Consumer, Regulatory, Employee, Client • Vendor Management – Lenders, Title, Suppliers, Warehouse Lines, BPO Clients etc. (DNC) • Quality Assurance and Quality Control • Legal Review – for risk mitigation Sutherland’s compliance policies and procedures ensure consistent operating guidelines that support the organization in complying with applicable federal consumer protection laws and regulations, both directly and through service providers. To further protect our clients each Sutherland employee engaged on a specific program as a dedicated employee are required to complete and adhere to the client’s compliance policies and procedures. The compliance policies and procedures provide employees with the information they need to perform their duties, protect the consumer and mitigate the client’s risks when engaging a third-party vendor. This may include applicable regulatory and legal citations and definitions, sample forms with instructions, and organization policy. Through industry monitoring, Sutherland will regularly review and update the compliance policies and procedures based upon new and revised federal and state consumer financial laws and regulations. Sutherland actively operates under the following certifications and practices: PCI, ISO 27001:2000, P-CMM, Six Sigma, HIPAA, GDPR, EU-U.S. Privacy Shield Framework and COPC. With over three decades of practitioner heritage, Sutherland has evolved to build its own Service Excellence Framework based on internal and external benchmarking of proven best practices.
Financial Services — NA | FCA regulated activities — describe your compliance approach for UK-regulated cardholder servicing including complaint handling. | Sutherland ensures complete regulatory, infosec and data privacy compliance through its internal compliance governance framework. Sutherland is fully FCA compliant in respect of its Insurance operations, with the controls, governance, and trained workforce that regulated insurance delivery requires. In relation to our Banking and Financial Services operations, we are currently progressing through our FCA compliance programme and are committed to achieving full compliance within a defined timeframe. 2. GDPR – European Privacy Standard Sutherland is committed to safeguarding personal data of employees and personal data handled by us on behalf of our clients by providing adequate protection and warranting its processes and systems operate in compliance with privacy principles enshrined in GDPR.
Financial Services — EMEA | FCA regulated activities — describe your compliance approach for UK-regulated cardholder servicing including complaint handling. | The compliance approach for UK regulated cardholder FCA regulated activities, including cardholder servicing and complaint handling would be based on several pillars of Sutherland compliace as below: 1. Sutherland has developed an in-house proprietary compliance quality framework for monitoring and evaluation of compliance adherence in our customers’ interactions. It covers both Outbound and Inbound Interactions. This aligns to all regulatory issues in relation to customer service and complaints. 2. Our Operational and Contract risk management policy is designed for the protection of Sutherland’s and the client’s interests against deficiency in operational processes and performance controls resulting in reasonably predictable and stable operations. The risk assessment covers the risks which impacts the interests of: • Clients • End users • Sutherland Sutherland ensures complete regulatory, infosec and data privacy compliance through its internal compliance governance framework. 3. Sutherland actively operates under the following certifications and practices: PCI, ISO 27001:2000, P-CMM, Six Sigma, HIPAA, GDPR, EU-U.S. Privacy Shield Framework and COPC. With over three decades of practitioner heritage, Sutherland has evolved to build its own Service Excellence Framework based on internal and external benchmarking of proven best practices. 4. GDPR – European Privacy Standard Sutherland is committed to safeguarding personal data of employees and personal data handled by us on behalf of our clients by providing adequate protection and warranting its processes and systems operate in compliance with privacy principles enshrined in GDPR. Sutherland is fully FCA compliant and licensed in respect of its Insurance operations, with the controls, governance, and trained workforce that regulated insurance delivery requires. In relation to our Banking and Financial Services operations, we are currently progressing through our FCA compliance programme and are committed to achieving full compliance within a defined timeframe.
Financial Services — EMEA | Germany (BaFin) and Netherlands (AFM/DNB) — describe relevant considerations for Hamburg and Barneveld operations. | Relevant considerations to be provided once the solution is finalised
(Add any additional regulatory area) | Add any further regulatory requirements, jurisdictional constraints, or compliance considerations relevant to your proposed delivery model that are not covered above. | Relevant considerations to be provided once the solution is finalised

## 9.0 Client EfficiencyAssumption
9.0 Client Efficiency Assumptions
9.1 Transformation Assumptions
At a per client level, what is the commitment from the vendor on offshore to onshore mix, consequent labor arbitrage %, cost reduction from AI & Digital Overlays, cost reduction from Productivity gains
Client Name | Offshore to Onshore Mix | Consequent Labor Arbitrage % | Cost Reduction from AI & Digital Overlays % | Cost Reduction from Productivity Gains % | Commitment to Certainty of Cost Savings as a %
US & Canada Clients Clients | 95:5 | 45% | 19.3% | 11.7% | 39.67%
Netherlands Clients | 95:5 | 5% | 19.3% | 11.7% | 39.67%
Germany Clients | 95:5 | 5% | 19.3% | 11.7% | 39.67%
United Kingdom Clients | 95:5 | 5% | 19.3% | 11.7% | 39.67%
Philippines Clients | 100:0 | 45% | 19.3% | 11.7% | 39.67%