## Project Timeline
Phase | Activity | Start Date | End Date | Type
RFP Administration | Align roles & responsibilities w/ Procurement | 2026-03-02 | 2026-03-10 | Activity
| Draft RFP document, appendices & SOW | 2026-03-02 | 2026-03-14 | Activity
| Launch RFP Intelligence Hub | 2026-04-01 | 2026-04-08 | Activity
| RFP issued to 6 vendors | 2026-03-17 | 2026-03-17 | Milestone
| Vendor Q&A responses distributed | 2026-03-25 | 2026-03-25 | Milestone
| Proposals & SOW redlines received (6 vendors) | 2026-03-27 | 2026-03-27 | Milestone
Workshop 1 — Vendor Credentials & Commercial (6 Vendors) | Prepare evaluation criteria, scoring mechanism, and pre-workshop memos | 2026-03-28 | 2026-03-31 | Activity
| Conduct Workshop 1 — 6 vendors (3 days) | 2026-03-31 | 2026-04-02 | Activity
| Post Workshop Debrief, Scoring, and Down-Selection Memo on RFP Intelligence Hub | 2026-04-02 | 2026-04-06 | Activity
| Decision Committee approves shortlist (6→3), notifies vendors of decision | 2026-04-07 | 2026-04-08 | Milestone
Workshop 2 — Migration, Rebadge, Tech & Offshoring (3 Vendors) | Prepare evaluation criteria, scoring mechanism, and pre-workshop memos | 2026-04-07 | 2026-04-12 | Activity
| Conduct Workshop 2 — 3 vendors (3 days) | 2026-04-13 | 2026-04-15 | Activity
| Post Workshop Debrief, Scoring, and Down-Selection Memo on RFP Intelligence Hub | 2026-04-15 | 2026-04-17 | Activity
| Decision Committee selects 2 finalists (3→2), notifies vendors of decision | 2026-04-17 | 2026-04-17 | Milestone
Workshop 3 — Commercial Alignment & Open Questions (2 Vendors) | Prepare evaluation criteria, scoring mechanism, and pre-workshop memos | 2026-04-17 | 2026-04-21 | Activity
| Conduct Workshop 3 — 2 vendors (2 days) | 2026-04-22 | 2026-04-23 | Activity
| Post Workshop Debrief, Scoring, and Recommendation on RFP Intelligence Hub | 2026-04-23 | 2026-04-25 | Activity
| Steering Committee meeting — approves path to award | 2026-04-21 | 2026-04-21 | Milestone
Workshop 4 — Technology Approach & Migration (2 Vendors) | Prepare FIS technology approach documentation & WS4 memos | 2026-04-21 | 2026-04-27 | Activity
| Conduct Workshop 4 — 2 vendors (2 days) | 2026-04-28 | 2026-04-30 | Activity
| Post-WS4 tech scoring, debrief & final proposal refinements | 2026-04-30 | 2026-05-07 | Activity
Contracting | Facilitate negotiation workshops (2 vendors) | 2026-05-05 | 2026-05-22 | Activity
| Compile & refine deal terms w/ FIS stakeholders | 2026-05-05 | 2026-06-10 | Activity
| Vendor ratification — Compliance & InfoSec | 2026-05-05 | 2026-06-15 | Activity
| Intent to Award | 2026-06-19 | 2026-06-19 | Milestone
Due Diligence | Facilitate FIS' due diligence of vendors | 2026-05-05 | 2026-06-15 | Activity
| Operations & Client SLA Due Diligence | 2026-05-12 | 2026-06-10 | Activity
| Technology Due Diligence | 2026-05-12 | 2026-06-10 | Activity
| HR & Workforce Due Diligence | 2026-05-19 | 2026-06-15 | Activity
Business Case | Business case sign-off to initiate RFP | 2026-03-02 | 2026-03-02 | Milestone
| Interim business case (post-RFP) | 2026-03-28 | 2026-04-24 | Activity
| Final Business Case (post-contracting) submitted for executive approval | 2026-06-19 | 2026-06-19 | Milestone